## START HERE
Client Communication & Deliverables Control — Master Template
Use this workbook to decide what the client receives, when reports are sent, who owns what, and which items remain internal know-how.
Subject | Description
Purpose | Keep client communication professional without giving away your full implementation IP.
Core rule | Client receives clarity, outcomes, reports, approvals, and access to their own data. Internal scenario logic/blueprints are shared only if contract/package says so.
When to use | After Phase 1 discovery and throughout Phases 2–6.
Recommended rhythm | Basic: milestone updates. Pro/Managed/Agentic: weekly short updates plus approval gates.
Important | Separate client deliverables from internal working files. Do not export Make blueprints containing credentials, prompts, or reusable framework logic unless explicitly sold/licensed.
Client Communication Progress (auto-computed)
Approval Gates — by Client Decision
Status | Meaning | Count
Approved | Gate formally signed off. | 0
Approved with comments | Signed off with conditions. | 0
Pending | Awaiting client decision. | 0
Rejected | Gate rejected. | 0
Not needed | Skipped intentionally. | 0
Communication Plan — by Status
Status | Meaning | Count
Planned | Communication scheduled. | 6
In Progress | Being prepared. | 0
Sent | Delivered to client. | 0
Approved | Client has approved. | 0
Blocked | Blocked — needs resolution. | 0
Not Needed | Not required for this project. | 0
Tip: client management is on track when (a) every Communication Plan item is 'Sent' or 'Approved' at the right time, and (b) every Approval Gate is 'Approved' (or 'Approved with comments') before its phase ends. 'Pending' gates approaching phase-end are the early warning signal.

## Communication Plan
Client Communication Plan
Define when and how the client receives updates/reports. Green columns are project-specific inputs.
Phase | Client Communication | Recommended Format | Frequency / Trigger | Client Approval Needed? | Owner | Status | Notes
Phase 1 Discovery | Discovery Summary / Initial Plan | 1–2 page summary or email | After discovery interview | Optional / recommended |  | Planned
Phase 2 Scope | MVP Scope Confirmation | Short report + scope table | Before blueprinting | Yes |  | Planned
Phase 3 Blueprint | Solution Blueprint Confirmation | Workflow diagram/summary + boundaries | Before build | Yes |  | Planned
Phase 4 Build | Build Progress Update | Short weekly or milestone update | Weekly or when blocked | Only if scope changes |  | Planned
Phase 5 Testing | Testing Summary + Go/No-Go | Test summary + defect status | Before launch | Yes |  | Planned
Phase 6 Managed Service | Monthly Service Report | Monthly KPI/report | Monthly | No, unless change requested |  | Planned

## Client Deliverables
Client Deliverables Register
Define what is delivered to the client versus what stays internal.
Deliverable | Phase | Client Receives? | Purpose | Format | Internal / Client / Hybrid | Share Level | Notes / Boundary
Discovery Summary | Phase 1 | Yes | Confirm needs, pain points, first MVP direction | PDF/email | Client | Summary only | No internal scoring details required
MVP Scope Confirmation | Phase 2 | Yes | Lock what is included/later/excluded | PDF/Excel excerpt | Client | Client-facing | Approval gate
Solution Blueprint Summary | Phase 3 | Yes | Confirm process, tools, approvals, security | PDF/diagram | Hybrid | Controlled detail | Avoid sharing reusable internal template logic
Full Make Blueprint Export | Phase 3/4 | Usually no | Technical implementation file | Make JSON | Internal | Do not share by default | Only under special paid handover/licensing
Build Progress Update | Phase 4 | Yes | Progress and blockers | Email/update | Client | Summary only
Test Results Summary | Phase 5 | Yes | Go/No-Go decision | PDF/table | Client | Client-facing | Include pass/fail and unresolved risks
Operations Dashboard | Phase 6 | Maybe | Visibility into results | CRM/Notion/Looker/Sheet | Client/Hybrid | Data/result access | Give access to client data, not necessarily build logic
Monthly Service Report | Phase 6 | Yes | Managed service value proof | PDF/email | Client | Client-facing | Runs, errors, improvements, next actions

## Ownership Models
Automation Ownership & Access Models
Choose the commercial/operational model before build. This protects both client trust and your IP.
Model | Description | Client Gets | You Keep | Best For | Risk / Warning | Recommended Position
Managed Service / Internal Build | Automation runs in your managed Make environment or agency workspace. | Results, reports, dashboard, approvals, documented process. | Scenario logic, prompts, reusable templates, vendor/API setup. | Basic/Pro managed packages. | Client dependency on you; must clarify continuity/exit terms. | Good default for managed service.
Client-Owned Workspace | Client owns Make/CRM/tools; you build inside their accounts. | Full operational access and ownership. | Your methodology, templates, documentation, service know-how. | Larger clients, compliance-heavy clients. | They can copy/modify logic; charge higher setup and limit template reuse. | Use for higher-priced implementation.
Hybrid | Client owns data/accounts; you manage automation layer. | Access to business data, CRM, reports; limited Make visibility. | Implementation framework, reusable scenario logic, prompts. | Most small businesses. | Needs clear SLA and exit plan. | Best balanced option.
[5 empty] | Undermines recurring revenue; must price high. | Offer only as premium package.
Note: VortexDeep does not offer a build-and-transfer / handover model, at any tier or price point — this is a deliberate policy, not an omission. Ownership is always offered as a licence (rows 6-7 above), never a transfer of the build. See VortexDeep_IP_and_Licensing_Policy_v01 §5 for why.

## Approval Gates
Client Approval Gates
Use this sheet to control what must be approved before moving forward.
Gate | Phase | Approval Item | Why Approval Matters | Client Decision | Date | Approved By | Notes | Completeness Status (AUTO)
G1 | After Phase 1 | Discovery Summary | Confirms problem and direction |  |  |  |  | Partial
G2 | After Phase 2 | MVP Scope | Prevents scope creep |  |  |  |  | Partial
G3 | After Phase 3 | Solution Blueprint + boundaries | Confirms how automation works and what AI may/may not do |  |  |  |  | Partial
G4 | After Phase 5 | Go/No-Go | Confirms readiness to launch |  |  |  |  | Partial
G5 | Phase 6 | Change request / improvement | Controls managed-service changes |  |  |  |  | Partial
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Gate Status at a Glance (auto-computed)
Status | Count | Meaning
Approved | 0 | Gate formally signed off.
Approved with comments | 0 | Approved with conditions or follow-ups.
Pending | 0 | Awaiting client decision.
Rejected | 0 | Gate rejected — requires rework.
Not needed | 0 | Skipped intentionally.
Total gates recorded | 5 | All rows with a Gate ID.

## Weekly Update Template
Weekly / Milestone Client Update Template
Copy this structure into email or report. Keep it short.
Subject | Description
Project
Reporting period
Overall status | Green / Yellow / Red
Done this period
In progress
Blocked / waiting for client
Risks / decisions needed
Next step
Target next milestone

## Monthly Report Template
Monthly Managed Service Report Template
Use after go-live for Managed/Agentic packages.
Section | Metric / Topic | Value / Notes | Client Meaning
Usage | Automation runs |  | How often the system worked
Usage | Items / inputs processed |  | Volume handled by automation
Quality | Correct processing results |  | Reliability of AI/rules
Quality | Human review cases |  | Where human judgment was needed
Reliability | Failed runs / errors |  | Operational stability
Reliability | Critical incidents |  | Any risk-impacting events
Improvements | Changes made |  | Service improvement delivered
Improvements | Recommended next improvements |  | Future value
Open Items | Client decisions needed |  | What blocks progress

## Access IP Matrix
Access, Ownership & IP Boundary Matrix
Define exactly what the client can access and what remains internal.
Item | Client Access? | Ownership | Reason | Boundary / Condition | Decision | Notes
Client Gmail/Email account | Yes | Client | Client business communication | Use OAuth/delegated access, not shared passwords
Client Instagram/Meta account | Yes | Client | Client channel | Client grants business/admin access
CRM/Notion client data | Yes | Client or shared | Operational visibility | Give data/results access
Make scenario editor | Maybe | Depends on model | Technical automation layer | Usually no in managed service; yes in client-owned/handover
Make blueprint export | Usually no | Your IP unless contracted otherwise | Reusable implementation logic | Only under paid handover/licensing; remove secrets first
AI prompts/classification logic | Maybe | Hybrid/IP | Core service know-how | Share high-level behavior, not full reusable prompt library unless agreed
API keys | No | You/client depending on account | Security | Never share keys; use connections/secrets
Reports/results | Yes | Client | Client value and transparency | Always share
Client accounting tool or document storage | Yes | Client | Finance / document automation data source | Connect via API or scheduled export; client retains full data ownership; no automated write-back without human confirmation.
Client CMS / social scheduling tool | Yes | Client | Content automation publishing target | API access for approved publishing actions only; client must approve each draft before publish — no direct auto-posting.
Client approval channels (email, Slack, Teams) | Yes | Client | Internal ops automation — approval routing and notifications | Outbound notification only; no access to other message threads or inboxes; approval routing per defined rules.