## START HERE
Phase 3 — Solution Blueprint
Purpose: convert Phase 2 MVP scope into a concrete automation design before building anything in Make, Zapier, n8n, CRM, Gmail, Meta, OpenAI, etc.
Step | What to do | Main sheet
1 | Copy final MVP decisions from Phase 2. | Phase2 to Phase3 Handoff
2 | Design the automation flow step-by-step. | Workflow Blueprint
3 | Define which data fields move through the system. | Data Field Map
4 | Define routing logic for each classification/category. | Routing Rules
5 | Choose tools and account ownership. | Tool Stack
6 | Define human approval, escalation, and safety boundaries. | Approval & Escalation
7 | Define credentials, access, logging, retention, and privacy rules. | Security & Access
8 | Define monitoring, errors, retries, and fallback behavior. | Error & Monitoring
9 | Summarize final blueprint before Phase 4 build. | Final Blueprint Summary
Color logic: Grey = fixed guidance, Green = fill during design workshop, Blue = PM/technical decision, Yellow = warning/boundary notes.
We planned this PM flow:
Phase 1 — Discovery / Analysis
Understand client needs, channels, risks, pain points, possible package direction.
Phase 2 — Scope Definition / MVP Design
Convert discovery answers into a clear first project scope.
Phase 3 — Solution Blueprint
Design workflow logic, tools, data fields, routing, approvals, security.
Phase 4 — MVP Build
Build the first safe automation version.
Phase 5 — Testing / Validation
Test real cases, edge cases, errors, wrong classifications, approvals.
Phase 6 — Go-live / Managed Service
Launch, monitor, maintain, improve, report.
Phase 3 Progress (auto-computed)
Workflow Blueprint — by Build Status
Status | Meaning | Count
Draft | Designed but not yet approved. | 22
Approved | Approved and ready for build. | 0
Later | Deferred to a later phase. | 0
Blocked | Blocked — needs resolution. | 0
Done | Build complete. | 0
Workflow Blueprint — by Completeness (col L)
Status | Meaning | Count
Empty | No fields filled. | 14
Partial | Some required fields still missing. | 0
Complete | All required fields filled. | 22
Security & Access — Required Before Build
Status | Meaning | Count
Yes | Decision finalized. | 7
No | Not required to lock before build. | 0
Later | Deferred. | 0
Final Blueprint Summary — Approved
Status | Meaning | Count
Yes | Section signed off. | 0
Partial | Partly signed off. | 0
No | Not yet signed off. | 10
Ready for Phase 4 build when (a) every Workflow Blueprint row is 'Complete' and 'Approved', (b) every Security & Access row is 'Yes', and (c) the Final Blueprint Summary sections are all 'Yes'.

## Workflow Step Designer
Workflow Step Designer — one step at a time
Use this when designing a single workflow step on the Workflow Blueprint and you're unsure about automation type, tool, approval rule, or risk. Fill the 6 yellow inputs; the blue cells suggest the design choices. PM judgment still final.
INPUTS — about this one step
# | Question | Allowed values | Answer
Q1 | Q1. Step purpose | Intake / Normalize / Classify / Route / Log / Draft reply / Send / Escalate / Monitor / Extract / Validate / Enrich / Generate content / Publish / Approve / Other | Classify
Q2 | Q2. Involves sensitive data? (health/legal/financial/emotional) | Yes / No / Sometimes | No
Q3 | Q3. Consequence if this step fails or acts wrongly | Low (annoyance) / Medium (lost lead) / High (legal/trust) | Medium
Q4 | Q4. AI involvement in this step | None / Classify only / Generate content / Take action | Classify only
Q5 | Q5. Reversibility of the action | Reversible / One-way (cannot undo) | Reversible
Q6 | Q6. Expected volume / frequency | Low / Medium / High | Medium
SUGGESTED DESIGN (auto-calculated)
# | Indicator | Suggested Value (formula) | Reasoning hint
O1 | Suggested Automation Type | AI | Take action → Agentic; Monitor → Managed; None → Traditional; otherwise AI.
O2 | Suggested Tool Family | AI API (OpenAI / Anthropic / Make AI) | Lookup by step purpose. Names match the Tool Stack sheet conventions.
O3 | Suggested Approval Rule | Optional (review when confidence low) | Sensitive / High consequence / One-way → Always. Send/Escalate → Required.
O4 | Risk Level | Medium | Sensitive or High-consequence elevate. One-way + AI = High.
O5 | Top Boundary Note | Standard: log inputs and outputs; fall back to Human Review on uncertainty. | The single biggest caution to record in the Workflow Blueprint Risk/Boundary column.
How to use this with the Workflow Blueprint:
1) Fill the 6 yellow inputs for ONE step you're designing.
2) Read the 5 blue suggestions.
3) Transfer the values into the matching row of Workflow Blueprint (Automation Type → col E; Tool → col D; Approval → col H; Risk → col J).
4) Use Routing Rules + Approval & Escalation sheets for category-level rules afterwards.
Caveat: this is decision support. Local context (client constraints, existing tools, contractual scope) overrides whenever it changes the picture.

## Phase2 to Phase3 Handoff
Phase 2 → Phase 3 Handoff
Use this sheet to transfer the final MVP scope and decisions into the blueprint design phase.
Item | Phase 2 Decision / Input (EDIT) | Blueprint Impact (POST) | Open Question | Owner | Status
MVP goal | Classify Gmail + website inquiries, route them, log in CRM, prepare human-approved drafts. | Determines core workflow modules. |  | PM | Draft
Included channels | Gmail, website form | Only these channels designed in MVP workflow. |  | PM | Draft
Excluded / later channels | Instagram later | Do not build Meta API in Phase 4 MVP. | Check API feasibility later. | PM | Later
Included categories | Booking, price question, lead, spam, complaint | Routing rules needed for each category. |  | PM | Draft
Human approval rule | All replies require approval. | Draft only; no automatic send module. |  | PM | Draft
Risk boundary | Sensitive content escalated; AI gives no advice. | Escalation route + safety prompt needed. |  | PM | Draft
Package direction | Basic / Pro mix | Simple build with AI classification and drafts. |  | PM | Draft

## Workflow Blueprint
Workflow Blueprint
Design the exact automation flow. This is the main Phase 3 working sheet.
Step No. | Process Step | Trigger / Input | Tool / Module Candidate | Traditional / AI / Agentic | Action Logic | Data Used / Created | Human Control | Output | Risk / Boundary | Build Status | Completeness Status (AUTO)
1 | Receive inquiry | Website form submitted or email received | Webhook / Gmail / IMAP | Traditional | Capture message and metadata. | sender, subject, message, timestamp, message_id | None | Normalized inquiry object | Do not lose original message. | Draft | Complete
2 | Normalize data | Raw email/form payload | Make tools / formatter | Traditional | Map fields into standard format. | channel, sender, content, source_id | None | Clean input object | Missing fields go to error route. | Draft | Complete
3 | Classify message | Normalized inquiry | OpenAI / Make AI tools | AI | Classify into approved taxonomy with confidence and reason. | classification, confidence, urgency | Review if low confidence. | Classification JSON | No advice; classify only. | Draft | Complete
4 | Route by category | Classification result | Router | Traditional | Send message to matching route. | classification, urgency | Human review for sensitive cases. | Selected route | Unknown category goes to Human Review. | Draft | Complete
5 | Log in CRM | Routed inquiry | Notion/Airtable/HubSpot | Traditional | Create or update record. | all key fields + status | Owner assigned | CRM record | Store minimum needed data. | Draft | Complete
6 | Prepare draft reply | Safe categories only | OpenAI / Gmail draft | AI | Generate short reply draft from approved rules/FAQ. | message, category, business rules | Human approval required | Draft email/message | No automatic sending in MVP. | Draft | Complete
7 | Escalate sensitive/urgent | Urgency or sensitive flag | Email/Slack/SMS notification | Traditional | Notify owner immediately. | classification, reason, source link | Human must handle | Escalation notification | No AI advice. | Draft | Complete
8 | Monitor result | Scenario completed or failed | Make logs / audit table | Managed | Write action log and notify on errors. | run_id, status, error | PM/service owner checks | Audit record | No silent failures. | Draft | Complete
| [Doc Processing] Receive document | Document arrives by email or upload (PDF / form / attachment) | Email connector / file handler / webhook | Traditional | Capture document and sender metadata; store original unmodified. | document_id, sender, filename, format, received_at | None | Raw document object with metadata | Preserve original; do not transform before extraction step. | Draft | Complete
| [Doc Processing] Extract structured fields | Raw document (PDF / image / form) | AI API (document parser / OCR / field extractor) | AI | Extract defined fields (e.g., invoice total, date, supplier name, line items). | extracted_fields, confidence_score, document_id | Flag low-confidence extractions for human review. | Structured data object | Define expected fields before build; mandatory error route for missing required fields. | Draft | Complete
| [Doc Processing] Validate extracted data | Structured data object from extraction step | Validation module (Make / n8n / custom rule logic) | Traditional | Check required fields present, format valid, values within expected range. | validation_result, error_list, document_id | Human review required for all validation failures. | Validated record or flagged exception | Never post a failed record to downstream system without human confirmation. | Draft | Complete
| [Doc Processing] Log to destination system | Validated record | CRM / Spreadsheet / Accounting connector | Traditional | Write confirmed record to target system; update status. | all extracted fields, validation_status, write_timestamp | Human confirms before posting financial data. | Logged entry in target system | Confirm before any financial write; log write result for audit. | Draft | Complete
| [Doc Processing] Notify on exceptions | Validation failure or extraction error | Email / Slack notification | Traditional | Alert owner of failed extractions, missing fields, or data mismatches. | document_id, error_list, exception_type, sender | Human must resolve all exceptions before data is used. | Exception notification sent | No silent failures; every exception logged and notified. | Draft | Complete
| [Content & Mktg] Receive source content | Client submits long-form post, article, or raw transcript | Email / form / shared drive connector | Traditional | Capture source text and context (platform targets, tone guide reference). | source_text, target_platforms, tone_guide_ref, content_id | None | Source content object | Validate source content is present and non-empty before triggering AI steps. | Draft | Complete
| [Content & Mktg] Generate platform-specific drafts | Source content object + tone guide | AI API (OpenAI / Anthropic / Make AI) | AI | Generate adapted draft for each target platform respecting character limits and tone guide. | source_text, platform, tone_guide, character_limits, content_id | Human reviews all drafts before any publishing action. | Draft posts per platform | No auto-publish; generate only; human must approve every post before it goes live. | Draft | Complete
| [Content & Mktg] Human review and approval | Draft posts per platform | CRM / email draft / approval channel | Traditional | Present drafts to owner for review; record approval or edit request per draft. | draft_id, review_status, reviewer, edited_content | Owner must explicitly approve or reject each draft before proceeding. | Approval decision per draft | Never proceed to publish without explicit approval; track rejection reasons. | Draft | Complete
| [Content & Mktg] Publish approved content | Approved draft + scheduling metadata | CMS / Social / Newsletter connector (scheduling tool) | Traditional | Publish or schedule approved content to target platform at specified time. | draft_id, platform, scheduled_at, published_at | Post-publish confirmation recommended. | Published post reference | Log post ID and timestamp; alert immediately on publish failure. | Draft | Complete
| [Content & Mktg] Log to content calendar | Published post reference | CRM / Spreadsheet / Content calendar tool | Traditional | Record published content in content calendar with full metadata. | post_id, platform, published_at, topic, status, content_id | None | Content calendar entry | Maintain complete audit trail for all published content. | Draft | Complete
| [Finance & Admin] Trigger from accounting data source | Scheduled export from accounting tool (Bexio / Banana / CSV file) | Email / file connector / API polling | Traditional | Receive periodic data export; parse overdue or pending records. | export_date, record_id, amount, due_date, client_ref, status | None | Parsed record list | Validate file format and expected fields before processing; reject malformed exports. | Draft | Complete
| [Finance & Admin] Identify actionable records | Parsed record list | Filter / router module (Make / n8n) | Traditional | Apply business rules to flag overdue invoices, missing data, or exception conditions. | record_id, days_overdue, exception_type, action_required | PM reviews and approves rule set before automation runs. | Filtered action list | Business rules must be approved before automation runs; define edge cases explicitly. | Draft | Complete
| [Finance & Admin] Send reminder or alert | Filtered action list | Email connector / notification tool | Traditional | Send templated reminder to client or internal alert to owner; log send result. | record_id, recipient, template_used, send_timestamp | PM approves first run; conditional auto-send after confirmed stable. | Reminder sent + send log | No payment processing; reminder only; log every send event. | Draft | Complete
| [Finance & Admin] Log action and result | Reminder sent or exception flagged | CRM / Spreadsheet / Audit log connector | Traditional | Record action taken, result, and any follow-up required. | record_id, action_taken, result, timestamp, follow_up_needed | None | Audit log entry | Maintain complete record of all finance-related automation actions. | Draft | Complete
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty

## Data Field Map
Data Field Map
Define the fields that must be captured, created, transformed, stored, or passed to tools.
Field Name | Source | Example Value | Required? | Used By | Stored Where | Retention / Privacy Note | Owner / Decision
source_channel | Webhook/Gmail | gmail / website_form | Yes | Routing, CRM, reports | CRM + audit log | Non-sensitive operational field.
source_message_id | Gmail/Form | email UID or form submission ID | Yes | Correlation, audit, deduplication | CRM + audit log | Important to avoid moving wrong email.
sender_name | Message payload | Anna Müller | Optional | CRM, draft reply | CRM | Personal data; store only if needed.
sender_email | Message payload | anna@example.com | Yes for email | Reply, CRM | CRM | Personal data; limit access.
subject | Email/form | Booking request | Optional | Classification, CRM | CRM | May contain personal data.
message_body | Email/form | I would like to book... | Yes | Classification, draft | CRM or limited log | Potentially sensitive; define retention.
classification | AI output | BOOKING_REQUEST | Yes | Router, reports | CRM + audit log | Internal processing field.
confidence | AI output | 0.87 | Yes | Fallback rule | CRM + audit log | Use threshold for review.
urgency | AI output/rules | normal / urgent | Yes | Escalation | CRM + audit log | Urgent must notify human.
status | Workflow | Pending Approval | Yes | CRM workflow | CRM | Operational status.

## Routing Rules
Routing Rules
Define what happens to each category/classification.
Category | Definition | Example Message | Allowed Automation | Human Approval? | Destination / Status | Auto Reply Allowed? | Fallback Rule | Notes
BOOKING_REQUEST | User wants to book appointment/service. | Do you have free time next week? | Classify + draft reply + create CRM item | Yes | Pending Approval | No in MVP | If unclear → Human Review
PRICE_QUESTION | User asks price/cost/package. | How much does it cost? | Classify + draft approved FAQ reply | Yes | Pending Approval | No in MVP | If service unclear → Human Review
LEAD | Potential business opportunity/customer. | I want to buy/use your service. | Classify + CRM item + notify owner | Yes | Lead Review | No in MVP | If uncertain → Human Review
COMPLAINT | Negative feedback or issue. | I am not satisfied... | Classify + escalate | Yes | Escalated | No | Always human
SENSITIVE | Health/legal/financial/private issue. | I feel very bad and need advice... | Classify + urgent/human route only | Yes | Human Review / Urgent | No | No AI advice
SPAM | Marketing, scam, irrelevant. | Buy followers now | Classify + move to spam-review | No, but review initially | Spam Review | No | Never delete in MVP
TEST | Internal testing. | test message | Classify + move test folder | No | Test | No | Keep test log

## Tool Stack
Tool Stack
Define tools, ownership, credentials, and purpose. This supports safe implementation in Phase 4.
Function | Preferred Tool | Alternative Tool | Account Owner | Credential Storage | Used For | MVP Required? | Risk / Note
Workflow orchestration | Make.com | n8n / Zapier | You or client workspace | Make connections/keychain | Scenario logic | Yes | Avoid hardcoded secrets.
Email intake | Gmail / IMAP | Outlook | Client | OAuth/IMAP connection | Receive and route emails | Yes | Client should own mailbox.
Website form intake | Webhook | Form plugin | Client/site owner | Webhook URL | Receive form submissions | Yes | Use correlation ID.
AI classification | OpenAI | Make AI / Anthropic | You/service account or client | Connection/secret, not raw header | Classify and draft | Yes | Rotate exposed keys.
CRM/logging | Notion | Airtable / HubSpot | Client or shared workspace | OAuth connection | Track inquiries | Yes | Access control needed.
Booking | Calendly / Google Calendar | Acuity | Client | OAuth connection | Booking link/slots | Later/Maybe | Agentic actions need approval.
Notifications | Email / Slack | Telegram | Client/team | Connection | Escalations/errors | Yes | Urgent route must work.

## Approval & Escalation
Approval & Escalation
Define where human control is mandatory and how escalations are handled.
Situation | AI Allowed? | Draft Allowed? | Auto-send Allowed? | Human Owner | Approval Channel | Escalation Time | Final Rule
Normal booking request | Yes, classify | Yes | No in MVP | Business owner | CRM/Gmail draft | Same day | Human approves before send.
Price/FAQ question | Yes, classify | Yes, from approved FAQ | No in MVP | Business owner | CRM/Gmail draft | Same day | Human approves before send.
Complaint | Classification only | No or very limited | No | Business owner | Email/phone alert | Immediate/priority | Human handles.
Sensitive personal content | Classification only | No advice | No | Business owner | Urgent alert | Immediate | Escalate; no AI advice.
Low confidence classification | Yes | No until reviewed | No | Business owner/PM | Human Review queue | Next review cycle | Fallback to human review.
Automation error | No | No | No | Service owner | Error notification | Immediate/next business hour | Stop risky action; log error.

## Security & Access
Security & Access
Define access, credentials, privacy, logging, and retention before build.
Control Area | Design Decision | Recommended Rule | Client Decision / Notes (EDIT) | Risk Level | Required Before Build?
API keys | No hardcoded keys in scenarios/exports. | Use Make connections/keychain or secure backend. |  | High | Yes
Client accounts | Client owns Gmail, calendar, social accounts. | Use granted access/OAuth where possible. |  | High | Yes
Scenario access | Limit who can edit production scenarios. | Only service owner/admins. |  | Medium | Yes
Data minimization | Store only necessary fields. | Avoid storing sensitive message body unless needed. |  | High | Yes
Retention | Define how long logs/messages stay in CRM. | Set client-specific retention rule. |  | Medium | Yes
Exports | Do not export/share blueprints with secrets. | Sanitize before sharing. |  | High | Yes
Audit log | Track actions taken by automation. | Write run_id, action, status, error. |  | Medium | Yes

## Error & Monitoring
Error & Monitoring
Design fallback behavior so automation does not fail silently or take wrong action.
Failure / Edge Case | Detection Method | Fallback Action | Notify Whom? | Log What? | Severity | Build Requirement
AI API error | HTTP error / timeout | Send item to Human Review; retry if safe | Service owner | run_id, payload id, error | High | Error route
Invalid JSON from AI | Parse error | Human Review; do not route automatically | Service owner | raw response + message id | High | JSON validation
Low confidence | confidence < threshold | Human Review | Business owner | classification + confidence | Medium | Threshold rule
Unknown category | classification not in list | Human Review | Service owner | category returned | Medium | Validation list
Duplicate message | same source_message_id | Skip or update existing record | None unless repeated | dedupe decision | Medium | Correlation ID
CRM write failure | API error | Retry; email notification | Service owner | record fields + error | High | Retry/error route
Email move failure | module error | Do not mark complete; notify | Service owner | email id + destination | Medium | Error route

## Final Blueprint Summary
Final Phase 3 Blueprint Summary
Complete this before starting Phase 4 build.
Section | Final Decision / Summary (EDIT) | Open Issue | Approved?
Workflow goal |  |  | No
Included channels |  |  | No
Core automation steps |  |  | No
Classification taxonomy |  |  | No
Routing rules |  |  | No
CRM/logging design |  |  | No
Human approval rules |  |  | No
Security/access decisions |  |  | No
Error/fallback handling |  |  | No
Ready for Phase 4 build? |  |  | No
Blueprint at a Glance (auto-computed)
Workflow steps designed |  |  | 22
Workflow steps — Approved |  |  | 0
Workflow steps — Done |  |  | 0
Data fields mapped |  |  | 10
Routing categories defined |  |  | 7
Tools selected as MVP-required |  |  | 6
Tools deferred (Later/Maybe) |  |  | 0
Approval rules defined |  |  | 6
Security controls — locked (Required=Yes) |  |  | 7
Error cases handled |  |  | 7
Total summary sections approved |  |  | 0

## Lists
Dropdown Lists
Internal lists used for consistent wording.
MVP Required? | Yes
No
Later
Maybe
Status | Draft
Approved
Later
Blocked
Done
Risk Level | Low
Medium
High
Automation Type | Traditional
AI
Managed
Agentic
Package | Basic
Pro
Managed
Agentic
Mixed