## START HERE
Phase 5 — Testing / Validation
Purpose: validate that the MVP built in Phase 4 is safe, reliable, and ready for go-live.
Step | What to do | Output
1 | Copy approved MVP modules from Phase 4 into the handoff sheet. | Clear list of items to test.
2 | Create test cases covering normal, edge, risk, and failure scenarios. | Test Case Matrix completed.
3 | Run each test and record actual result, pass/fail, defect, owner, and fix notes. | Evidence-based validation.
4 | Review AI classification quality separately: category, confidence, fallback, hallucination risk. | AI Validation completed.
5 | Review approval, escalation, audit, error handling, and security behavior. | Safety checks completed.
6 | Only approve go-live if critical issues are closed and success criteria are met. | Go / No-Go decision.
We planned this PM flow:
Phase 1 — Discovery / Analysis
Understand client needs, channels, risks, pain points, possible package direction.
Phase 2 — Scope Definition / MVP Design
Convert discovery answers into a clear first project scope.
Phase 3 — Solution Blueprint
Design workflow logic, tools, data fields, routing, approvals, security.
Phase 4 — MVP Build
Build the first safe automation version.
Phase 5 — Testing / Validation
Test real cases, edge cases, errors, wrong classifications, approvals.
Phase 6 — Go-live / Managed Service
Launch, monitor, maintain, improve, report.
Phase 5 Progress (auto-computed)
Test Case Matrix — by Pass/Fail
Status | Meaning | Count
Pass | Test passed. | 0
Fail | Test failed. | 0
Partial | Partial pass — close but not exact. | 0
Not Tested | Not yet run. | 0
Blocked | Cannot test. | 0
Approval Escalation Tests — by Pass/Fail
Status | Meaning | Count
Pass | Approval/escalation behavior correct. | 0
Fail | Failed — risky behavior detected. | 0
Partial | Partial pass. | 0
Not Tested | Not yet run. | 0
Error Monitoring Tests — by Pass/Fail
Status | Meaning | Count
Pass | Fallback behaved correctly. | 0
Fail | Fallback failed. | 0
Partial | Partial pass. | 0
Not Tested | Not yet run. | 0
Defect Log — by Status
Status | Meaning | Count
Open | Defect open. | 2
In Progress | Being worked. | 0
Retest | Fixed; awaiting retest. | 0
Closed | Closed (fixed and verified). | 0
Accepted Risk | Closed without fix — risk accepted. | 0
Go No-Go Checklist — by Status
Status | Meaning | Count
Pass | Gate passed. | 0
Fail | Gate failed. | 0
Partial | Gate partly met. | 0
Not Tested | Gate not yet evaluated. | 0
Ready for Phase 6 go-live when (a) every Test Case Matrix row is 'Pass' (or 'Partial' with documented exception), (b) every Approval and Error test is 'Pass', (c) every Defect Log row is 'Closed' or 'Accepted Risk', and (d) every Go No-Go gate is 'Pass'.

## Test Result Triage Helper
Test Result Triage Helper — one test, one verdict
Use this AFTER running a single test, before recording Pass/Fail on the Test Case Matrix. Fill the 6 yellow inputs; the blue cells suggest verdict, severity, whether a defect is needed, go-live blocker status, and recommended next action. PM judgment still final.
INPUTS — about this one test run
# | Question | Allowed values | Answer
Q1 | Q1. Did the actual result match the expected? | Exactly / Close (minor differences) / Partially / No / Errored before completion | Exactly
Q2 | Q2. Type of mismatch (if any) | None / Wrong category / Wrong action / Wrong route / Unsafe behavior / Other | None
Q3 | Q3. Reproducibility | Always / Sometimes / Once (could not reproduce) | Always
Q4 | Q4. Safety / privacy impact if this bug ships | None / Minor / Major / Critical (data loss, sensitive harm, legal) | None
Q5 | Q5. Affected scope | Single test / Single category / Whole workflow / Multiple workflows | Single test
Q6 | Q6. Test scenario type | Normal / Edge / Risk / Failure / Error simulation | Normal
SUGGESTED VERDICT (auto-calculated)
# | Indicator | Suggested Value (formula) | Reasoning hint
O1 | Verdict (Pass/Fail) | Pass | Exactly match → Pass. Unsafe behavior → Fail regardless. Partial → Partial.
O2 | Severity (if defect) | None | Critical safety → Critical. Wrong action/route → High. Wrong category → Medium.
O3 | Defect needed? | No | Exact pass → No. Close → Maybe (log only). Otherwise → Yes.
O4 | Go-live blocker? | No | Critical safety always blocks. Risk/Failure scenarios that fail block. Whole-workflow scope blocks.
O5 | Recommended next action | Mark Pass; move to next test. | Single concrete next step based on the combination.
How to use this with the Test Case Matrix:
1) Run one test (TC-### row on Test Case Matrix).
2) Fill the 6 yellow inputs here.
3) Read the 5 blue suggestions; record the Pass/Fail on the matrix.
4) If a defect is needed → open a Defect Log row with the suggested severity and blocker status.
Caveat: this is decision support. PM judgment overrides — especially for 'Conditional' go-live blocker calls.

## Phase4 to Phase5 Handoff
Phase4 to Phase5 Handoff
Transfer the built MVP components and expected behavior from Phase 4.
Build Component | Expected Behavior | Source from Phase4 | Test Priority | Risk Level | Ready for Test? | Notes | Owner
Trigger / Intake | Receives only intended trigger inputs (messages, documents, events, or data records). | Phase4 Module Build Plan | High | Medium
Data Normalization | Maps source input fields into standard format correctly (channel, type, content, timestamp, source_id). | Phase4 Data Map | High | Medium
AI Classifier | Returns valid JSON with category, confidence, reason, action. | Phase4 AI Prompt Config | High | High
Router | Routes each classification to the correct branch. | Phase4 Module Build Plan | High | Medium
CRM / Log | Creates correct record with status and audit fields. | Phase4 Build Backlog | Medium | Medium
Human Approval | Drafts or actions are held for approval where required. | Phase4 Approval Design | High | High
Error Handling | Failed modules create error status and alert owner. | Phase4 Error Build | High | High

## Test Case Matrix
Test Case Matrix
Main testing sheet: define cases, run tests, record evidence, defects, and decisions.
Test ID | Scenario Type | Input Channel | Test Input / Message | Expected Classification | Expected Action | Human Approval Required? | Expected Output / Evidence | Actual Result | Pass/Fail | Defect ID | Severity | Owner | Fix / Retest Notes | Retest Result | Completeness Status (AUTO)
TC-001 | Normal | Website form | Customer asks where to buy product in Switzerland. | LEAD | Create CRM item, move email to Leads, no auto-send. | Yes | CRM item + folder move + audit log | [7 empty] | Partial
TC-002 | Out-of-scope | Website form | Distributor request for Bangladesh. | SEEKER | Create SEEKER record, use approved short reply draft or no reply depending policy. | Yes | SEEKER status + audit log | [7 empty] | Partial
TC-003 | Spam | Website form | Generic SEO offer with suspicious links. | SPAM | Move to spam-review folder, do not delete. | No | Email moved + audit log | [7 empty] | Partial
TC-004 | Sensitive | Gmail | Client asks for personal medical/therapy advice. | SENSITIVE / HUMAN_REVIEW | Escalate to human, no AI advice. | Yes | Human review alert | [7 empty] | Partial
TC-005 | Error | Gmail | Force AI API failure or invalid JSON response. | ERROR | Stop action, log error, notify owner. | Yes | Error log + notification | [7 empty] | Partial
TC-D01 | Non-normal | Document upload (email attachment) | [Invoice PDF] Supplier: ABC GmbH, CHF 4'850, due 2026-07-15 | INVOICE / EXTRACT | Extract all required fields → validate → log to accounting tool; flag mismatches for review. | Yes | Extracted data logged; mismatch → exception alert sent |  |  |  | Medium |  |  |  | Partial
TC-D02 | Non-normal | Approval request form submission | [Purchase request] CHF 1'200 office equipment — route to manager for approval | APPROVAL_REQUEST | Route to approver → send notification and log; reminder if no response within 24h. | Yes | Notification sent; request logged; reminder scheduled at +24h |  |  |  | Low |  |  |  | Partial
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty

## AI Validation
AI Validation
Validate AI behavior separately from workflow execution.
Test ID | Message | Expected Category | AI Category | Confidence | Reason Quality | JSON Valid? | Fallback Triggered? | Hallucination / Unsafe Content? | Decision | Notes
AI-001 | Booking request / product purchase question. | LEAD or BOOKING
AI-002 | Distributor / reseller request outside target country. | SEEKER
AI-003 | Complaint or angry message. | COMPLAINT / HUMAN_REVIEW
AI-004 | Sensitive therapy or medical question. | SENSITIVE / HUMAN_REVIEW
AI-005 | Empty or unclear message. | UNKNOWN / HUMAN_REVIEW
AI-D01 | [Invoice PDF] Supplier ABC GmbH, CHF 4'850, due 2026-07-15 | INVOICE / EXTRACT — fields: supplier, amount, due_date, currency
AI-D02 | Source blog post (800 words) submitted for repurposing to Instagram and LinkedIn | CONTENT_REPURPOSE — drafts per platform; never auto-publish

## Approval Escalation Tests
Approval & Escalation Tests
Validate that human control works where required.
Rule / Case | Expected Behavior | Test Input | Actual Behavior | Pass/Fail | Risk if Failed | Fix Required | Owner
AI draft reply | Draft is created but not sent automatically. |  |  |  | Wrong message may be sent.
Sensitive case | Escalates to human review and no advice is generated. |  |  |  | Client safety/privacy risk.
Complaint | Marked urgent or human review. |  |  |  | Reputation risk.
Low confidence | Routes to Human Review. |  |  |  | Misclassification risk.
Agentic action | No calendar/CRM action without allowed rule and approval. |  |  |  | Uncontrolled action risk.

## Error Monitoring Tests
Error & Monitoring Tests
Validate failure behavior before go-live.
Failure Scenario | Expected Fallback | How to Simulate | Actual Result | Pass/Fail | Alert Sent? | Audit Log Created? | Severity | Fix Notes
AI API unavailable | Stop workflow, no wrong action, notify owner. | Disable key / use test bad endpoint. |  |  |  |  | High
Invalid AI JSON | Route to error/human review. | Force malformed response. |  |  |  |  | High
CRM/Notion unavailable | Do not lose message; create error notification. | Disconnect CRM temporarily. |  |  |  |  | High
Duplicate message | Avoid duplicate CRM item or mark duplicate. | Send same message twice. |  |  |  |  | Medium
Wrong/empty required field | Human review or error status. | Submit empty email/message. |  |  |  |  | Medium

## Defect Log
Defect Log
Track all issues found during testing until closed.
Defect ID | Found In Test ID | Description | Severity | Status | Owner | Root Cause | Fix Action | Retest Date | Retest Result | Go-live Blocker?
D-001 |  |  | High | Open
D-002 |  |  | Medium | Open

## Go No-Go Checklist
Go / No-Go Checklist
Final validation gate before Phase 6 go-live.
Gate | Criteria | Status | Evidence / Notes | Owner
Scope | All MVP in-scope items tested.
Critical Defects | No open critical/high go-live blockers.
AI Safety | Sensitive/low-confidence cases route to human review.
Approval | No risky auto-send or autonomous action without approval.
Error Handling | Errors generate notifications and audit logs.
Security | No exposed API keys or hardcoded secrets.
Client Review | Client reviewed and accepted MVP behavior.
Go-live Decision | GO / NO-GO / GO WITH LIMITATIONS
Go-Live Readiness Summary (auto-computed)
Test cases defined |  |  |  | 7
Test cases — Pass |  |  |  | 0
Test cases — Fail |  |  |  | 0
Test cases — Not Tested |  |  |  | 0
Defects logged |  |  |  | 2
Defects — Open or In Progress |  |  |  | 2
Defects — Closed / Accepted Risk |  |  |  | 0
Go-live blockers (col K = Yes) |  |  |  | 0
Approval/Escalation tests — Pass |  |  |  | 0
Error/Monitoring tests — Pass |  |  |  | 0
Go No-Go gates — Pass |  |  |  | 0

## Lists
PassFail | Severity | Status | RiskLevel | MVPRelevant | Package
Pass | Critical | Open | Low | Yes | Basic
Fail | High | In Progress | Medium | No | Pro
Partial | Medium | Retest | High | Later | Managed
Not Tested | Low | Closed |  |  | Agentic
Blocked |  | Accepted Risk |  |  | Mixed