## START HERE
AI Automation Managed Services — Phase 2 Scope Definition / MVP Design
Purpose | Use this workbook after Phase 1 Discovery to convert client answers into a controlled MVP scope.
Core question | What exactly will we build first, what is excluded, and what must stay under human control?
Main workflow | 1) Transfer relevant Phase 1 findings → 2) Decide scope → 3) Define MVP → 4) Set automation boundaries → 5) Produce final scope summary.
MVP meaning | Minimum Viable Product: the smallest useful and safe first automation version that solves the main client problem without unnecessary complexity.
Important rule | Do not include everything the client mentioned. Include only what is valuable, safe, feasible, and needed for the first version.
Color guide
Grey | Fixed guidance / reference fields — normally do not edit.
Green | Client/discovery input — copied or summarized from Phase 1.
Yellow | Internal package / automation decision support.
Blue | PM decision fields — fill after analysis.
Recommended step-by-step use
1 | Open 'Phase1 to Phase2 Handoff' and summarize the strongest findings from Phase 1.
2 | Use 'Phase2 Scope Builder' to decide Yes / Later / No for each requirement.
3 | Use 'MVP Definition' to write the first version of the solution in plain language.
4 | Use 'Automation Boundary' to define what AI may classify, draft, send, or escalate.
5 | Use 'Priority Scoring' if there are too many possible features.
6 | Complete 'Final Scope Summary' as the project-ready output.
We planned this PM flow:
Phase 1 — Discovery / Analysis
Understand client needs, channels, risks, pain points, possible package direction.
Phase 2 — Scope Definition / MVP Design
Convert discovery answers into a clear first project scope.
Phase 3 — Solution Blueprint
Design workflow logic, tools, data fields, routing, approvals, security.
Phase 4 — MVP Build
Build the first safe automation version.
Phase 5 — Testing / Validation
Test real cases, edge cases, errors, wrong classifications, approvals.
Phase 6 — Go-live / Managed Service
Launch, monitor, maintain, improve, report.
Phase 2 Progress (auto-computed)
By MVP Decision (Phase2 Scope Builder col F)
Status | Meaning | Count
Yes | Included in MVP. | 10
Later | Deferred to a later phase. | 3
No | Excluded from project. | 1
Needs clarification | Open question — needs client confirmation. | 0
By Completeness (Phase2 Scope Builder col N)
Status | Meaning | Count
Empty | No fields filled yet. | 85
Partial | Some required fields still missing. | 0
Complete | All required fields filled. | 14
By Workflow Status (Phase2 Scope Builder col M)
Status | Meaning | Count
Open | Decision pending. | 13
Decided | Decision locked. | 1
Blocked | Cannot proceed — needs resolution. | 0
Needs client confirmation | Waiting on client. | 0
Tip: ready for Phase 3 when (a) every Scope Builder row is 'Complete', (b) zero rows remain 'Needs clarification', and (c) the Final Scope Summary narrative fields are filled.

## Scope Decision Helper
Scope Decision Helper — one requirement at a time
Use this for a single candidate requirement when you're unsure whether to include it in MVP, defer it, or exclude it. Fill the 9 yellow inputs; the blue cells suggest MVP Decision, Package Direction, Approval rule, Risk flag, and a top caution. PM judgment still final — this just removes the staring-at-a-blank-cell moment.
INPUTS — about this one requirement
# | Question | Allowed values | Answer
Q1 | Q1. Requirement (short label) | Free text — e.g., 'Draft replies to booking questions'
Q2 | Q2. Business Value (1-5, 5 = critical to client) | 1 / 2 / 3 / 4 / 5 | 3
Q3 | Q3. Risk Level from Phase 1 | Low / Medium / High / Critical | Medium
Q4 | Q4. Feasibility (1-5, 5 = easy, APIs ready) | 1 / 2 / 3 / 4 / 5 | 3
Q5 | Q5. Complexity (1-5, 5 = very complex) | 1 / 2 / 3 / 4 / 5 | 3
Q6 | Q6. Sensitive topic? (health, legal, financial, emotional) | Yes / No | No
Q7 | Q7. Phase 1 flagged it as MVP-relevant? | Yes / Later / No / Unknown | Unknown
Q8 | Q8. AI autonomy desired | Classify only / Classify + draft / Draft + auto-send / Multi-step agent | Classify + draft
Q9 | Q9. Time pressure to deliver | None / Some / High | Some
SUGGESTED DECISIONS (auto-calculated)
# | Indicator | Suggested Value (formula) | Reasoning hint
O1 | Suggested MVP Decision | Needs clarification | Risk Critical → No. Phase 1 Unknown → Needs clarification. Low feasibility → Later. High value + manageable → Yes.
O2 | Suggested Package Direction | Pro | Multi-step → Agentic. Auto-send → Pro/Managed. Drafts → Pro. Classify only → Basic.
O3 | Approval rule (product flag) | Required (drafts reviewed before send) | Sensitive or high-risk → always approve. Classify-only → no approval needed.
O4 | Risk flag | Watch — review approval and audit before go-live. | Surfaces blockers and high-risk combinations early.
O5 | Top caution | No major caution flagged. | The single biggest watch-out for this requirement.
How to use this with the Scope Builder:
1) Fill the 9 yellow inputs for one candidate requirement.
2) Read the 5 blue suggestions.
3) Open Phase2 Scope Builder, add a new row with the requirement and PM-confirm the values (Risk, MVP Decision, Package, Approval, Status). The Helper does not write to the Scope Builder automatically.
4) Use Priority Scoring for cross-comparison when you have many candidates.
Caveat: the Helper is decision support, not authority. PM judgment overrides whenever local context (client trust, contract scope, existing tools) changes the picture.

## Phase1 to Phase2 Handoff
Phase 1 Finding / Flag | Client Answer / Evidence (GREEN) | Risk Level (GREEN) | Possible Package Direction (YELLOW) | Phase 2 Question to Decide (BLUE) | Decision Owner | Notes
Channels used | Example: Gmail, Instagram, website form | Medium | Pro | Which channels enter MVP first? | PM + Client | Start with highest-value / easiest channel.
Main pain point | Example: too much time answering booking questions | Low | Basic | Which pain must MVP solve first? | PM | Avoid solving secondary problems in first version.
Sensitive data | Example: clients sometimes share personal/health details | High | Managed | Which messages require human-only handling? | PM + Client | No direct AI advice for sensitive topics.
Approval preference | Example: client wants to approve all outgoing replies | Medium | Pro | Can AI create drafts only? | Client | Human approval protects quality.
Reporting need | Example: client wants weekly overview of missed inquiries | Low | Managed | Is reporting in MVP or later? | PM | Could be Managed package driver.

## Phase2 Scope Builder
ID | Requirement / Need from Phase 1 | Source / Evidence | Business Value | Risk Level | MVP Decision | Package Direction | Automation Method Candidate | Human Approval Required? | Scope Boundary / Constraint | Output / Decision | Next Action | Status | Completeness Status (AUTO)
1 | Classify website form inquiries | Website form sends subject + message | Reduce manual sorting | Low | Yes | Basic | AI classification | No | Only classify, no auto-send | Build as MVP core | Define categories | Open | Complete
2 | Route spam/test messages | Many low-value messages | Reduce inbox noise | Low | Yes | Basic | Rule-based automation | No | Move to review folder, do not delete | Include in MVP | Create folder labels | Open | Complete
3 | Draft replies to booking questions | Client loses time replying | Save response time | Medium | Yes | Pro | AI draft reply | Yes | Draft only; human sends | Include if approved | Collect approved answer templates | Open | Complete
4 | Instagram DM intake | Client receives social messages | No missed leads | Medium | Later | Pro | AI classification | Yes | Depends on Meta access/API | Phase 2 or later | Check account/API feasibility | Open | Complete
5 | Auto-send replies to sensitive topics | Sensitive content possible | Risk reduction | High | No | Not applicable | Manual only | Always | Never auto-send | Excluded | Document boundary | Decided | Complete
6 | [Lead Pipeline] Score and route inbound leads by source and value | CRM / web form / email submissions | Faster follow-up; no missed high-value leads | Medium | Yes | Pro | AI classification + CRM logging | Conditional | CRM enrichment only; no auto-send of proposals or follow-up sequences | Leads routed and logged; owner notified per category | Map lead categories and routing rules | Open | Complete
7 | [Document Processing] Extract invoice data and log to accounting | Supplier invoices received by email (PDF attachments) | Saves 3–4 h/week on manual data entry | Medium | Yes | Basic | AI classification | Yes | Extract and log only; human confirms before posting to accounting system | Invoice fields extracted and logged; mismatches flagged for review | Define required extraction fields and acceptable error threshold | Open | Complete
8 | [Content & Marketing] Repurpose blog post into platform-specific draft formats | Client produces weekly long-form post or article | Saves 2 h/week; extends reach without extra writing effort | Low | Yes | Pro | AI draft reply | Yes | Draft only; no auto-publish; one source format per run in MVP | Draft posts for Instagram, LinkedIn, and newsletter ready for owner review | Agree on approved tone guide and platform templates | Open | Complete
9 | [Internal Ops] Route approval requests with automated reminder | Staff submit requests by email or intake form | Reduces approval delays from days to hours | Low | Yes | Basic | Rule-based automation | Yes | Routing and notification only; no auto-approve under any circumstance | Request logged; approver notified; reminder sent if no reply within 24h | Define routing rules, approver list, and reminder timing | Open | Complete
10 | [Reporting] Weekly KPI digest pulled from CRM and calendar | Existing CRM and calendar data sources | Saves 1 h/week; ensures consistent management visibility | Low | Later | Managed | Monitoring/reporting | No | Read-only data access only; no write actions | Weekly email digest with agreed KPIs sent to defined recipients | Agree on KPIs, recipients, and report cadence | Open | Complete
11 | [Finance & Admin] Send payment reminders for overdue invoices | Accounting tool export or spreadsheet (Bexio / Banana / CSV) | Reduces overdue accounts; replaces manual follow-up | Medium | Yes | Managed | Rule-based automation | Conditional | Reminder only; no payment processing or accounting write-back | Reminder sent at day 7 and day 14 after due date | Define overdue threshold and approved reminder text | Open | Complete
12 | [Scheduling] Propose available calendar slots in reply to meeting request | Incoming email or form requesting an appointment | Removes scheduling back-and-forth; faster booking confirmation | Low | Later | Agentic | Agentic calendar action | Yes | Read-only calendar access in MVP; no auto-booking or event creation | Draft reply with 3 available slots ready for human to review and send | Confirm calendar API access and permission scope | Open | Complete
13 | [Customer Support] Triage and route support tickets by urgency and type | Support inbox or shared helpdesk email | Reduces response time; urgent cases handled with priority | Medium | Yes | Pro | AI classification | Always | Triage and routing only; no auto-reply to customers in MVP | Ticket classified, tagged, and routed to correct agent queue | Define ticket categories and urgency keywords | Open | Complete
14 | [E-commerce] Send order confirmation and shipping update notifications | E-commerce platform order events / webhooks | Reduces WISMO inquiries; improves customer experience | Low | Yes | Basic | Rule-based automation | No | Outbound notification only; no order modification or refund logic | Order confirmation and shipping update sent automatically on trigger | Confirm webhook access and notification templates | Open | Complete
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty

## MVP Definition
Phase 2 Output — MVP Definition
MVP Element | Instruction | Example | Your Phase 2 Decision (EDIT)
MVP Goal | Write one clear sentence describing the first useful automation version. | Example: Reduce manual checking of Gmail and website inquiries by classifying messages, logging them, and preparing human-approved replies.
Primary Business Problem | What problem must be solved first? | Example: Client loses time sorting and answering repeated booking questions.
Included Channels | Only channels in first version. | Example: Gmail + website form. Instagram later.
Included Message Categories | Categories handled in MVP. | Example: Booking, price question, spam/test, general inquiry.
Included Automations | Concrete automations included. | Example: classify, route, create CRM item, draft reply.
Human Approval Points | Where human must approve before action. | Example: all outgoing replies must be reviewed.
Explicit Exclusions | What is not included now. | Example: WhatsApp, payment handling, automatic sending, sensitive advice.
Success Criteria | How we know MVP works. | Example: 90%+ correct routing in test set; zero auto-sent sensitive replies.
Package Direction | Internal direction only, not final offer. | Example: Basic now, Pro later.

## In-Out Scope Matrix
Item / Feature | In Scope | Out of Scope | Later | Reason / Boundary | Client Confirmation Needed?
Gmail intake | Yes |  |  | Core MVP channel | No
Website form intake | Yes |  |  | Core MVP channel | No
Instagram DM intake |  |  | Yes | Needs API/access check | Yes
Automatic email sending |  | Yes |  | Not in first version due to approval risk | Yes
AI draft replies | Yes |  |  | Draft only, human sends | Yes
Sensitive advice replies |  | Yes |  | Human-only | Yes

## Automation Boundary
Message / Task Type | AI May Classify? | AI May Summarize? | AI May Draft? | AI May Send? | AI May Update CRM? | Human Approval Rule | Escalation / Boundary Note
Booking request | Yes | Yes | Yes | No | Yes | Human approves reply | No autonomous booking in MVP unless approved.
Price question | Yes | Yes | Yes | No | Yes | Human approves reply | Use approved FAQ only.
Spam/Test | Yes | No | No | No | Yes | No approval needed for folder routing | Move to review folder; do not delete.
Complaint | Yes | Yes | No | No | Yes | Always human | Mark urgent / review.
Sensitive personal/health/legal/financial topic | Yes | Maybe | No | No | Yes | Always human | No advice; escalate to business owner.

## Priority Scoring
Priority Scoring — rank candidate features for MVP
Score each candidate feature on 5 dimensions (1-5). The score, class, and suggested MVP decision are calculated automatically. Lower complexity is better — that dimension is subtracted, not added. Empty rows are blank (no fake scores).
ID | Feature / Requirement | Business Value (1-5) | Urgency (1-5) | Risk Reduction (1-5) | Complexity (1-5) (subtracts!) | Data/API Feasibility (1-5) | Priority Score (auto) | Priority Class (auto) | MVP Decision (your call) | Suggested MVP (auto)
1 | Classify Gmail inquiries | 5 | 5 | 3 | 2 | 5 | 16 | Must have | Yes | Yes
2 | Classify Instagram DMs | 4 | 3 | 3 | 4 | 2 | 8 | Could have | Later | Later
3 | AI draft replies | 4 | 4 | 3 | 3 | 4 | 12 | Should have | Yes | Yes
4 | Auto-send replies (sensitive) | 3 | 2 | 1 | 4 | 4 | 6 | Won't have now | No | No
How the formulas work
Priority Score |  |  | Formula: (Business Value + Urgency + Risk Reduction + Feasibility) − Complexity. Range: −4 to 20.
Priority Class — Must have |  |  | Score ≥ 14. Strong candidate for MVP.
Priority Class — Should have |  |  | Score 10-13. Solid candidate.
Priority Class — Could have |  |  | Score 7-9. Optional / nice-to-have.
Priority Class — Won't have now |  |  | Score < 7. Defer or exclude.
Suggested MVP |  |  | Must/Should → 'Yes'. Could → 'Later'. Won't → 'No'. You can override in the MVP Decision column.
Complexity |  |  | This is the only dimension that REDUCES the score. High complexity = harder = lower priority.
Tip: enter the feature name in column B first — that activates the formulas. Leaving B blank keeps the row empty (no fake '0' score).

## Final Scope Summary
Final Phase 2 Scope Summary
Client / Project Name |  | Date | 2026-06-23
MVP Package Direction |  | Prepared by
MVP Goal
Included Channels
Included Automations
Human Approval Rules
Out of Scope
Key Risks / Boundaries
Success Criteria
Next Phase Trigger | Proceed to Phase 3 Solution Blueprint when client confirms this scope.
Scope at a Glance (auto-computed)
In Scope (MVP=Yes) |  |  | 10
Deferred (MVP=Later) |  |  | 3
Excluded (MVP=No) |  |  | 1
Needs client confirmation |  |  | 0
High-risk items (Risk=High or Critical) |  |  | 1
Items requiring human approval |  |  | 8
Total scope items defined |  |  | 14

## Lists
Risk Level | MVP Decision | Package Direction | Automation Method | Human Approval | Status | Priority
Low | Yes | Basic | Rule-based automation | Yes | Open | Must have
Medium | Later | Pro | AI classification | No | Decided | Should have
High | No | Managed | AI summary | Conditional | Blocked | Could have
Critical | Needs clarification | Agentic | AI draft reply | Always | Needs client confirmation | Won't have now
|  | Mixed | Human approval workflow
|  | Not applicable | CRM logging
Monitoring/reporting
Agentic calendar action
Agentic CRM action
Manual only