## START HERE
Phase 4 — MVP Build
Convert the approved Phase 3 blueprint into a controlled, testable first automation build. Build only the approved MVP, not the final scaled system.
Step | Activity | Instruction | Use Sheet
1 | Transfer design | Copy final Phase 3 decisions into the handoff sheet. | Phase3 to Phase4 Handoff
2 | Break into tasks | Create concrete build items and dependencies. | Build Backlog
3 | Configure modules | Build trigger, normalizer, AI classifier, router, CRM, notification/draft, audit and error handler. | Module Build Plan
4 | Secure access | Set up connections safely. Never store secrets in workbook or hardcoded modules. | Credentials & Access
5 | Configure prompts | Define schema, categories, confidence and fallback rules. | AI Prompt Config
6 | Prepare tests | Create seed cases for formal Phase 5 validation. | Test Seed Cases
7 | Checklist | Confirm MVP build is ready before testing. | Build Checklist
We planned this PM flow:
Phase 1 — Discovery / Analysis
Understand client needs, channels, risks, pain points, possible package direction.
Phase 2 — Scope Definition / MVP Design
Convert discovery answers into a clear first project scope.
Phase 3 — Solution Blueprint
Design workflow logic, tools, data fields, routing, approvals, security.
Phase 4 — MVP Build
Build the first safe automation version.
Phase 5 — Testing / Validation
Test real cases, edge cases, errors, wrong classifications, approvals.
Phase 6 — Go-live / Managed Service
Launch, monitor, maintain, improve, report.
Phase 4 Progress (auto-computed)
Build Backlog — by Status
Status | Meaning | Count
Not Started | Build not begun. | 12
In Progress | Build in progress. | 0
Done | Build complete. | 0
Blocked | Cannot proceed — needs resolution. | 0
Module Build Plan — by Status
Status | Meaning | Count
Not Started | Module not built yet. | 10
In Progress | Module being built. | 0
Done | Module ready. | 0
Blocked | Module blocked. | 0
Build Checklist — by Pass status
Status | Meaning | Count
Pass | Checklist item verified. | 0
Pending | Not yet verified. | 0
Fail | Failed — needs rebuild or fix. | 0
N/A | Not applicable for this project. | 0
Credentials & Access — by Status
Status | Meaning | Count
Not Started | Credential not set up. | 6
Set up | Credential connected. | 0
Verified | Connection tested and verified. | 0
Blocked | Cannot proceed. | 0
Ready for Phase 5 testing when (a) every Build Backlog item is 'Done', (b) every Module Build Plan row is 'Done', (c) every Credentials row is 'Verified', and (d) every Build Checklist item is 'Pass'.

## Build Item Readiness Helper
Build Item Readiness Helper — should I build this now?
Use this BEFORE starting any build item. Fill the 6 yellow inputs about the item; the blue cells suggest whether to build now, the priority, mandatory pre-build checks, Phase 5 test priority, and the top safety boundary. PM judgment still final.
INPUTS — about this one build item
# | Question | Allowed values | Answer
Q1 | Q1. Build item category | Module / Credential / Prompt / Audit-error / Test / Other | Module
Q2 | Q2. Dependency status | All met / Some pending / Blocked | All met
Q3 | Q3. Risk level (from Phase 3 blueprint) | Low / Medium / High | Medium
Q4 | Q4. AI involvement in this item | None / Classify only / Generate content / Take action | Classify only
Q5 | Q5. Security touch points | Routine / OAuth setup / Secret handling / Sensitive data | Routine
Q6 | Q6. Phase 3 blueprint approval status | Yes / Partial / No / Unknown | Yes
SUGGESTED VERDICT (auto-calculated)
# | Indicator | Suggested Value (formula) | Reasoning hint
O1 | Build verdict | GO — proceed with build. | Phase 3 must be Yes and dependencies met. Anything else → Hold or Block.
O2 | Priority recommendation | P2 (standard sprint priority) | Credentials and audit-error are foundational. High-risk AI items also P1.
O3 | Mandatory pre-build checks | Confirm trigger source ID; no auto-delete; error route attached. | Single most-important pre-build action for this combination.
O4 | Phase 5 test priority | Standard test set (happy + 1-2 edge cases) | High risk / agentic / sensitive → must test. Low-risk passive → smoke only.
O5 | Top safety boundary | Standard: write audit row each run; no destructive actions on error. | The biggest single safety rule for this build item.
How to use this with the Build Backlog:
1) Pick one B-### item from the Build Backlog.
2) Fill the 6 yellow inputs.
3) Read the 5 blue suggestions; transfer Priority and Risk into the backlog row.
4) Use Mandatory pre-build checks as a sanity gate before starting work.
Caveat: this is decision support. Real PM judgment (client trust, contract scope, team availability) may override the recommendation.

## Phase3 to Phase4 Handoff
Phase 3 → Phase 4 Handoff
Use this to preserve scope. Build decisions must come from the approved Phase 3 blueprint.
Handoff Area | Approved Phase 3 Decision | Build Impact | Owner | Status | Open Issue / Comment
MVP goal |  | Defines what the first build must achieve |  | Not Started
Included data sources / channels |  | Defines triggers/connections to configure |  | Not Started
Included processing categories |  | Defines classifier labels, extraction schema, or routing rules |  | Not Started
Excluded functions |  | Defines what must not be built yet |  | Not Started
Human approval points |  | Defines draft/review/not-send logic |  | Not Started
Tool stack |  | Defines Make apps and external services |  | Not Started
Data fields |  | Defines CRM/log/audit fields |  | Not Started
Security/access rules |  | Defines credentials, ownership and permissions |  | Not Started
Error handling rules |  | Defines fallback notifications and no-destructive-actions logic |  | Not Started

## Build Backlog
Phase 4 Build Backlog
Main MVP implementation task list. Use Status/Priority/Dependency to control the build.
ID | Build Item | Description | Source Decision | Priority | Status | Owner | Dependency | Risk | Done Criteria | Notes | Completeness Status (AUTO)
B-001 | Create scenario shell | Create project scenario with naming convention and version. | Phase3 blueprint | High | Not Started |  | None | Low | Scenario created and named correctly |  | Complete
B-002 | Configure trigger/input | Configure webhook/email/form trigger based on approved MVP. | Included channels | High | Not Started |  | B-001 | Medium | Trigger receives exact intended payload |  | Complete
B-003 | Normalize input fields | Map incoming data to standard fields. | Data field map | High | Not Started |  | B-002 | Medium | All required fields present |  | Complete
B-004 | Configure AI classifier | Build AI classification step with strict JSON output. | Routing rules | High | Not Started |  | B-003 | Medium | Classifier returns valid JSON and labels |  | Complete
B-005 | Add validation/fallback | Handle invalid or low-confidence AI response. | Error rules | High | Not Started |  | B-004 | High | Unknown/invalid routes to Human Review |  | Complete
B-006 | Build router paths | Route each category to correct action. | Routing rules | High | Not Started |  | B-004 | Medium | Each category has safe path |  | Complete
B-007 | Create CRM/log record | Create Notion/Airtable/CRM record. | Data field map | High | Not Started |  | B-006 | Medium | Record contains key fields/status |  | Complete
B-008 | Create draft/notification | Prepare draft or notification without unsafe auto-send. | Approval rules | Medium | Not Started |  | B-006 | Medium | Human receives clear draft/task |  | Complete
B-009 | Move/label message | Move or label exact source message only. | Tool stack | Medium | Not Started |  | B-006 | High | No wrong message moved |  | Complete
B-010 | Add audit log | Log classification, action and status. | Monitoring | High | Not Started |  | B-006 | Medium | Each run writes audit row |  | Complete
B-011 | Add error handler | Notify on failure and avoid destructive actions. | Error rules | High | Not Started |  | B-006 | High | Failure creates alert/status Error |  | Complete
B-012 | Prepare test seed cases | Prepare cases for Phase 5 testing. | Test plan | Medium | Not Started |  | B-004 | Low | All categories have sample messages |  | Complete

## Module Build Plan
Scenario / Module Build Plan
Translate the workflow into concrete modules. One row per Make/app module or component.
Step | Module / Component | Purpose | Input | Output | Configuration Needed | Safety Rule | Status | Test Ref | Notes | Completeness Status (AUTO)
1 | Trigger | Receive trigger input | Trigger payload (message, document, event, or data record) | Raw payload | Connection, trigger filter, exact ID capture | Never lose source ID | Not Started | TC-001 |  | Complete
2 | Normalizer / Mapper | Standardize fields | Raw payload | Standard fields | Map source fields into standard format (channel, type, content, timestamp) | Required fields cannot be empty | Not Started | TC-002 |  | Complete
3 | AI Classifier | Classify input / extract structured data | Standard fields | JSON classification | Prompt, schema, temperature, model | No free text outside JSON | Not Started | TC-003 |  | Complete
4 | JSON Parser / Validator | Validate AI output | Classifier result | Parsed fields | Schema, required values, fallback | Invalid → Human Review | Not Started | TC-004 |  | Complete
5 | Router | Select action path | Parsed classification | Selected path | Route filters per category | No category without fallback | Not Started | TC-005 |  | Complete
6 | CRM/Database Create | Log record / entry | Mapped fields | CRM item | Database/table fields | Store minimum necessary data | Not Started | TC-006 |  | Complete
7 | Draft/Notify | Prepare next action | Input + classification or extraction result | Draft/task/alert | Template, recipient, approval flow | No auto-send unless approved | Not Started | TC-007 |  | Complete
8 | Move/Label Message | Organise or route source item | Exact source item ID (message ID, document ID, record ID) | Folder/label update | Folder names, ID mapping | Use exact message ID only | Not Started | TC-008 |  | Complete
9 | Audit Log | Record execution | All prior outputs | Audit row | Log table/sheet fields | Every run logged | Not Started | TC-009 |  | Complete
10 | Error Handler | Catch failures | Error event | Alert + error log | Error route, notification recipient | No deletion on error | Not Started | TC-010 |  | Complete

## Credentials & Access
Credentials & Access Register
Record access setup without storing secrets. Never paste API keys or passwords into this workbook.
Service / Tool | Credential Type | Owner | Stored Where | Access Level | Rotation / Revocation Plan | Status | Do NOT Store Here | Notes
Make.com | Workspace access | Provider or client | Make team/workspace | Admin/Editor/Viewer | Remove user or transfer scenario ownership | Not Started | Passwords, API keys
Gmail / Google Workspace | OAuth connection | Client preferred | Make connection / OAuth | Minimum required scopes | Client can revoke OAuth access | Not Started | Passwords
Instagram / Meta | OAuth / Business integration | Client | Meta Business / Make connection | Page messaging access only | Remove app/business permission | Not Started | Access tokens
OpenAI | API key | Provider or client | Make secure connection/keychain or backend proxy | Limited project key | Rotate key if exposed; monitor usage | Not Started | Raw key
CRM / Notion / Airtable | OAuth/API connection | Client preferred | Make connection | Create/update only where needed | Revoke integration from workspace | Not Started | Raw key
Calendar / Booking | OAuth connection | Client | Make connection / native integration | Read availability / create draft booking if approved | Revoke OAuth app | Not Started | Passwords

## AI Prompt Config
AI Prompt / Rule Configuration
Define AI behavior as a controlled build asset: prompts, schema, categories, confidence, fallback and approvals.
Prompt ID | Use Case | Model / Tool | Input Fields | Required Output Schema | Allowed Categories | Temperature | Confidence Threshold | Fallback Rule | Human Approval? | Status | Notes
P-001 | Message classification | OpenAI / Make AI | subject, message, channel | classification, confidence, urgency, reason, suggested_action, requires_human_review | Client-specific taxonomy | 0 | 0.80 | Below threshold → Human Review | Yes | Not Started
P-002 | Reply draft | OpenAI / Make AI | message, category, FAQ, tone | draft_subject, draft_body, risk_note | Safe categories only | 0.2 | 0.85 | If sensitive → no draft, escalate | Yes | Not Started
P-003 | Summary for CRM | OpenAI / Make AI | message, classification | one_sentence_summary, client_need | All non-spam categories | 0 | 0.80 | Invalid → raw message note | No | Not Started
P-004 | Urgency detection | OpenAI / Make AI | message | urgency, escalation_reason | normal, important, urgent | 0 | 0.90 | Urgent → notify human immediately | Yes | Not Started
P-005 | Document field extraction | OpenAI / Make AI | document_text, field_schema, document_type | extracted_fields, confidence, missing_fields, validation_status | Defined field schema per document type (invoice, contract, form) | 0 | 0.85 | Missing required field → flag for human review; do not post to system | Yes | Not Started | Validate extracted fields before any downstream write; error route mandatory.
P-006 | Content repurposing / draft generation | OpenAI / Make AI | source_content, target_platform, tone_guide, character_limit | draft_content, platform_format, risk_note | Approved target platforms only | 0.3 |  | Human review required before any publish action; never auto-publish | Yes | Not Started | One source per run; draft only — never publish without explicit human approval.

## Audit & Error Build
Audit Log and Error Handling Build
Build logging and error handling as part of MVP, not afterthought.
Item | What to Build | Required Fields / Logic | Reason | Status | Owner | Notes
Audit log row | Write one log row per run | timestamp, source_id, channel, classification, confidence, action_taken, status | Supports monitoring and client trust | Not Started
Error log row | Write one row per failed run | timestamp, scenario, module, error_message, source_id, recovery_status | Supports support/debugging | Not Started
Failure notification | Send alert to provider/admin | error summary, affected client, run link, next action | Prevents silent failures | Not Started
Fallback route | Route unknown/invalid cases to Human Review | invalid JSON, missing field, low confidence, unrecognized category | Avoids unsafe automation | Not Started
No destructive action rule | Do not delete source messages automatically | move/label instead of delete | Protects client data | Not Started
Exact message matching | Use source ID or correlation ID | no latest-unread matching in production | Avoids wrong message moved/replied | Not Started

## Test Seed Cases
Test Seed Cases for Phase 5
Prepare representative messages during build. These become the starting point for formal Phase 5 testing.
Test ID | Category | Sample Input Message | Expected Classification | Expected Action | Risk | AI Draft? | Auto-Send? | Notes
TC-001 | Lead / Booking | Hello, I would like to book an appointment next week. | BOOKING / LEAD | Create CRM item + draft booking reply | Low | Yes | No
TC-002 | Price question | Can you tell me your prices? | PRICE_QUESTION | Create draft FAQ reply | Low | Yes | No
TC-003 | Sensitive message | I have a personal problem and need advice now. | SENSITIVE / HUMAN_REVIEW | Escalate to human, no advice | High | No | No
TC-004 | Complaint | I did not receive an answer and I am unhappy. | COMPLAINT | Human review + important flag | Medium | Maybe | No
TC-005 | Spam | Buy followers cheap now. | SPAM | Move to spam-review folder | Low | No | No
TC-006 | Unclear | Hi | UNKNOWN / HUMAN_REVIEW | Human review | Medium | No | No
TC-007 | Test message | This is a test form submission. | TEST | Route to test folder/log | Low | No | No
TC-008 | Document Processing | [Invoice PDF received] Supplier: ABC GmbH, CHF 4'850, due 2026-07-15 | INVOICE / DOCUMENT | Extract fields → validate → log to accounting; flag mismatches for review | Medium | Yes (field extraction) | No | Example for document extraction automation — adapt field schema per project
TC-009 | Content & Marketing | [Source article submitted] Product launch blog post (800 words); targets: Instagram, LinkedIn, newsletter | CONTENT_REPURPOSE | Generate platform-specific drafts → route to human review → publish only after approval | Low | Yes | No | Example for content repurposing — never auto-publish; human approval required before every post
TC-010 | Internal Ops / Approval | [Approval request submitted] Purchase: CHF 1'200, office equipment, submitted by T. Müller | APPROVAL_REQUEST | Route to approver → send notification + log; reminder if no reply within 24h | Low | No | No | Example for approval routing automation — no auto-approve under any circumstance

## Build Checklist
Phase 4 Build Completion Checklist
Complete this before starting formal Phase 5 testing.
Check ID | Checklist Item | Pass? | Evidence / Link / Comment | Owner | Date
C-001 | Scenario/workflow name and version are clear
C-002 | Trigger receives the correct source message/payload
C-003 | No hardcoded API keys or passwords are visible in modules
C-004 | Client-owned connections are used where appropriate
C-005 | AI classifier returns strict valid JSON
C-006 | Low-confidence/invalid outputs route to Human Review
C-007 | No unsafe automatic sending is enabled unless approved
C-008 | CRM/database record is created correctly
C-009 | Audit log is written for each run
C-010 | Error handler creates alert and error log
C-011 | Exact message ID/correlation logic is confirmed
C-012 | Test seed cases are prepared for Phase 5
Build at a Glance (auto-computed)
Backlog items defined | [5 empty] | 12
Backlog items — Done | [5 empty] | 0
Modules planned | [5 empty] | 10
Modules — Done | [5 empty] | 0
Credentials registered | [5 empty] | 6
Credentials — Verified | [5 empty] | 0
AI prompts defined | [5 empty] | 6
AI prompts — Done | [5 empty] | 0
Audit/Error items defined | [5 empty] | 6
Test seed cases prepared | [5 empty] | 8
Build Checklist items — Pass | [5 empty] | 0
Build Checklist items — Pending/Fail | [5 empty] | 0

## Change Log
Build Change Log
Track changes to prompts, routing, module settings and security decisions during implementation.
Change ID | Date | Area | Change Description | Reason | Impact | Approved By | Status
CH-001
CH-002
CH-003