## START HERE
AI Automation Managed Services — Phase 6: Go-live & Managed Service
Purpose | Launch the tested MVP safely, monitor real operation, maintain service quality, and improve the automation over time.
Input from Phase 5 | Go/No-Go decision, validated test cases, known defects, approval rules, final tested MVP, client acceptance notes.
Main output | Live automation + monitoring plan + support model + monthly review/improvement loop.
How to use | 1) Fill Phase5 to Phase6 Handoff. 2) Complete Go-live Checklist. 3) Define Monitoring & Support. 4) Track issues in Operations Log. 5) Use Monthly Review for managed service improvements.
Color guide | Grey = fixed guidance. Green = fill during go-live/operation. Blue = PM/managed-service analysis. Yellow = decision/risk note.
Important | Phase 6 is not 'finished and forgotten'. It is the operational service layer: monitoring, client support, quality control, reporting, and controlled improvements.
Phase 6 Sheet Map
Sheet | Use
Phase5 to Phase6 Handoff | Transfer final testing status and launch prerequisites.
Go-live Checklist | Confirm readiness before production activation.
Launch Plan | Plan launch date, responsibilities, rollback, client communication.
Monitoring & Support | Define what is monitored, frequency, owner, alert route, SLA.
Operations Log | Track live issues, failed runs, misclassifications, client requests.
Monthly Review | Review performance and decide improvements.
Improvement Backlog | Controlled list of changes after go-live.
Client Handover | Access, documentation, training, ownership, acceptance.
Final Phase6 Summary | Executive summary of launched managed service.
We planned this PM flow:
Phase 1 — Discovery / Analysis
Understand client needs, channels, risks, pain points, possible package direction.
Phase 2 — Scope Definition / MVP Design
Convert discovery answers into a clear first project scope.
Phase 3 — Solution Blueprint
Design workflow logic, tools, data fields, routing, approvals, security.
Phase 4 — MVP Build
Build the first safe automation version.
Phase 5 — Testing / Validation
Test real cases, edge cases, errors, wrong classifications, approvals.
Phase 6 — Go-live / Managed Service
Launch, monitor, maintain, improve, report.
Phase 6 Progress (auto-computed)
Go-live Checklist — by Status
Status | Meaning | Count
Not Started | Not begun. | 15
In Progress | In progress. | 0
Done | Complete. | 0
Blocked | Blocked. | 0
Waiting Client | Waiting on client action. | 0
Operations Log — by Status
Status | Meaning | Count
Not Started | Logged but not triaged. | 0
In Progress | Being worked. | 0
Done | Resolved. | 0
Blocked | Cannot proceed. | 0
Waiting Client | Waiting on client. | 0
Improvement Backlog — by Status
Status | Meaning | Count
Not Started | Logged, not triaged. | 0
In Progress | Being assessed or built. | 0
Done | Delivered. | 0
Blocked | Cannot proceed. | 0
Waiting Client | Waiting on client. | 0
Monthly Review — by Status
Status | Meaning | Count
OK | Metric in target. | 0
Watch | Trending — monitor. | 0
Action Needed | Triggered improvement action. | 0
Not Measured | Not yet measured. | 0
Client Handover — by Status
Status | Meaning | Count
Not Started | Not begun. | 8
In Progress | In progress. | 0
Done | Complete. | 0
Blocked | Blocked. | 0
Waiting Client | Waiting on client. | 0
Managed service is healthy when (a) Go-live Checklist is 'Done', (b) Client Handover is 'Done', (c) Operations Log issues are being resolved within target time, and (d) Monthly Review items are mostly 'OK' or 'Watch', with 'Action Needed' items flowing into Improvement Backlog.

## Operations Issue Triage Helper
Operations Issue Triage Helper — one incident or request at a time
Use this when a live issue, error, misclassification, or client request comes in. Fill the 6 yellow inputs; the blue cells suggest priority, rollback decision, client communication, owner, and top corrective action. Then log the issue in the Operations Log with those values.
INPUTS — about this one issue
# | Question | Allowed values | Answer
Q1 | Q1. Issue type | Failed Run / Wrong Classification / Wrong Processing Result / Client Request / Security/Access / API/Tool Limit / Enhancement / Other | Failed Run
Q2 | Q2. Impact scope | Single message / Single category / Whole channel / All workflows | Single message
Q3 | Q3. Frequency | One-off / Sporadic / Persistent (repeating) | One-off
Q4 | Q4. Safety / data impact | None / Minor / Major / Critical (legal, sensitive data harm, trust) | None
Q5 | Q5. Cause known? | Yes (root cause clear) / Partially / No (investigating) | Partially
Q6 | Q6. Client awareness | Not noticed / Noticed not complained / Complained / Asked us directly | Not noticed
SUGGESTED RESPONSE (auto-calculated)
# | Indicator | Suggested Value (formula) | Reasoning hint
O1 | Priority | P4 (next monthly review) | Critical safety / all-workflows → P1. Client complained / Major → P2. Sporadic minor → P3.
O2 | Rollback decision | Not needed — fix forward. | Critical → Rollback now. Major + persistent → Consider. Otherwise fix forward.
O3 | Client communication | None needed — fix silently and log. | Apologize for Critical/Major or client complaints. Inform if client noticed. Silent for minor one-offs.
O4 | Owner | Service Provider | Most operational issues → Service Provider. Client requests/enhancements → Shared.
O5 | Top corrective action | Check audit log + error route; confirm retry safe; ensure no duplicate or wrong action. | Single concrete next step tailored to issue type and cause.
How to use this with the Operations Log / Improvement Backlog:
1) When a live issue, error, or client request comes in, fill the 6 yellow inputs.
2) Read the 5 blue suggestions.
3) For operational issues → log in Operations Log with the suggested Priority, Owner, Status. Transfer the corrective action.
4) For enhancements / client requests → log in Improvement Backlog with the suggested Priority and a note about package impact.
Caveat: this is decision support. Live judgement may override — e.g., client trust, contract terms, or 'this is the third time this happened' may warrant escalating priority.

## Lists
Status | Go Decision | Priority | Risk | Package | Frequency | Owner Role | Issue Type
Not Started | Go | Low | Low | Basic | Real-time | Client Owner | Failed Run
In Progress | Conditional Go | Medium | Medium | Pro | Hourly | Service Provider | Wrong Classification
Done | No-Go | High | High | Managed | Daily | Shared | Client Request
Blocked |  | Critical | Critical | Agentic | Weekly | External Vendor | Security/Access
Waiting Client |  |  |  | Mixed | Monthly |  | API/Tool Limit
[5 empty] | On demand |  | Enhancement

## Phase5 to Phase6 Handoff
Item | Phase 5 Result / Evidence (EDIT) | Open Issue? (EDIT) | Required Before Go-live (EDIT) | Owner (EDIT) | Go-live Impact | PM Decision / Notes (POST)
Go/No-Go result |  |  |  |  | Defines whether launch is possible
Critical defects |  |  |  |  | Critical defects must be closed or accepted
AI classification quality |  |  |  |  | Confirms whether AI route is safe enough
Approval/escalation tests |  |  |  |  | Confirms human-control behavior
Error monitoring tests |  |  |  |  | Confirms failure notifications work
Client acceptance |  |  |  |  | Client confirms tested workflow is acceptable
Known limitations |  |  |  |  | Must be documented before launch
Rollback requirement |  |  |  |  | Needed if production launch fails

## Go-live Checklist
Category | Checklist Item | Why it matters | Status (EDIT) | Owner (EDIT) | Due Date (EDIT) | Evidence / Link (EDIT) | Go-live Blocker? (EDIT) | PM Notes (POST) | Completeness Status (AUTO)
Access | Client-owned accounts connected with approved access | Avoids dependency on private accounts | Not Started | [5 empty] | Partial
Access | API keys/secrets not hardcoded in scenario | Prevents exposed credentials | Not Started | [5 empty] | Partial
Access | Revocation/rotation process documented | Allows emergency access control | Not Started | [5 empty] | Partial
Scenario | Production scenario duplicated/backed up before launch | Allows rollback | Not Started | [5 empty] | Partial
Scenario | Test data removed from production CRM/logs | Keeps client data clean | Not Started | [5 empty] | Partial
Scenario | Triggers/schedule configured correctly | Ensures automation runs as intended | Not Started | [5 empty] | Partial
Safety | Human approval active where required | Prevents unsafe auto-replies/actions | Not Started | [5 empty] | Partial
Safety | Fallback route for unknown/low-confidence cases active | Prevents wrong routing | Not Started | [5 empty] | Partial
Safety | Sensitive/urgent escalation route active | Protects high-risk cases | Not Started | [5 empty] | Partial
Monitoring | Error handler and alerts active | Enables fast issue response | Not Started | [5 empty] | Partial
Monitoring | Audit log writing correctly | Enables traceability | Not Started | [5 empty] | Partial
Client | Client knows how to review/approve items | Supports adoption | Not Started | [5 empty] | Partial
Client | Client knows what is excluded from MVP | Prevents scope misunderstanding | Not Started | [5 empty] | Partial
Documentation | Workflow documentation delivered | Supports maintenance | Not Started | [5 empty] | Partial
Documentation | Known limitations documented | Avoids false expectations | Not Started | [5 empty] | Partial
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty

## Launch Plan
Launch Element | Decision / Plan (EDIT) | Owner (EDIT) | Date / Time (EDIT) | Dependencies | Rollback Plan (EDIT) | Client Communication (EDIT) | PM Notes (POST)
Launch date/time |  |  |  | No critical blockers; client acceptance
Production activation method |  |  |  | Scenario schedule/webhook activation defined
First live monitoring window |  |  |  | Service provider available during first live run
Client notification before launch |  |  |  | Client knows what will happen and when
Rollback trigger |  |  |  | Define what failure requires rollback
Rollback steps |  |  |  | Backup scenario exists
Post-launch review meeting |  |  |  | At least first operational review scheduled

## Monitoring & Support
Monitoring Item | What to Check | Frequency (EDIT) | Owner Role (EDIT) | Alert Trigger / Threshold (EDIT) | Alert Channel (EDIT) | Response Target (EDIT) | Escalation Rule (EDIT) | Notes
Scenario execution | Failed or incomplete runs | Daily | Service Provider | Any failed run | Email/Make notification | Same business day | Escalate if repeated
AI classification quality | Wrong category or low-confidence pattern | Weekly | Service Provider | More than 2 wrong cases/week | Monthly review / email | Next review cycle | Update prompt/rules
Human approval queue | Items waiting too long | Daily | Client Owner | Items older than agreed limit | Email/CRM status | Client-defined | Notify client owner
CRM/logging | Records created correctly | Weekly | Service Provider | Missing records or wrong fields | Email | Same business day | Fix mapping
Sensitive escalation | Urgent/sensitive messages routed correctly | Weekly | Shared | Any missed escalation | Immediate alert | Immediate review | Pause risky route if needed
API usage/costs | Unusual usage or credit consumption | Weekly/Monthly | Service Provider | Above budget/normal range | Email/report | Next review cycle | Adjust schedule/model
Client feedback | Complaints, confusion, new needs | Monthly | Shared | Client feedback received | Meeting/email | Monthly | Add to improvement backlog

## Operations Log
Date | Issue / Event Type | Description | Impact | Priority | Owner | Status | Root Cause | Corrective Action | Preventive Action | Client Informed? | Closed Date

## Monthly Review
Review Period | Metric / Topic | Target / Expectation | Actual Result (EDIT) | Status (EDIT) | Insight / Interpretation (POST) | Decision / Improvement (POST) | Owner | Due Date
| Number of failed runs | 0 critical / low failed-run rate
| Wrong classifications | Low and decreasing
| Messages routed to human review | Useful, not excessive
| Average response/approval delay | Within client expectation
| Client time saved | Clear positive value
| New recurring request types | Identify improvement needs
| Cost / API usage | Within agreed budget
| Client feedback | Positive or actionable

## Improvement Backlog
ID | Improvement Request | Source | Business Value | Risk / Complexity | Package Impact | Priority | Status | MVP or Later | Owner | Decision | Notes | Completeness Status (AUTO)
IMP-001 | [11 empty] | Empty
IMP-002 | [11 empty] | Empty
IMP-003 | [11 empty] | Empty
IMP-004 | [11 empty] | Empty
IMP-005 | [11 empty] | Empty
IMP-006 | [11 empty] | Empty
IMP-007 | [11 empty] | Empty
IMP-008 | [11 empty] | Empty
IMP-009 | [11 empty] | Empty
IMP-010 | [11 empty] | Empty
IMP-011 | [11 empty] | Empty
IMP-012 | [11 empty] | Empty
IMP-013 | [11 empty] | Empty
IMP-014 | [11 empty] | Empty
IMP-015 | [11 empty] | Empty
IMP-016 | [11 empty] | Empty
IMP-017 | [11 empty] | Empty
IMP-018 | [11 empty] | Empty
IMP-019 | [11 empty] | Empty
IMP-020 | [11 empty] | Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty
Empty

## Client Handover
Handover Area | What is Delivered / Explained | Client Owner (EDIT) | Service Provider Owner (EDIT) | Status (EDIT) | Evidence / Link (EDIT) | Notes
Workflow overview | Explain what automation does and does not do |  |  | Not Started
Review/approval process | Show where client reviews AI drafts or escalated items |  |  | Not Started
Access ownership | Confirm client owns business-critical accounts |  |  | Not Started
Support process | Explain how to report issues/change requests |  |  | Not Started
Monitoring/reporting | Explain monitoring frequency and monthly review |  |  | Not Started
Limitations | Explain exclusions and known limitations |  |  | Not Started
Emergency fallback | Explain what happens if automation fails |  |  | Not Started
Acceptance confirmation | Client confirms launch acceptance |  |  | Not Started

## Final Phase6 Summary
Field | Summary / Decision (EDIT) | Notes
Client / Project
Package Direction |  | Basic / Pro / Managed / Agentic / Mixed
Go-live Date
Live Channels
Live Automations
Human Approval Points
Monitoring Model
Support Model
Known Limitations
Next Review Date
Next Improvement Priorities
Final Phase 6 Status |  | Launched / Conditional / Not Launched
Phase 6 at a Glance (auto-computed)
Go-live checklist items — Done |  |  | 0
Go-live blockers — Yes |  |  | 0
Client Handover items — Done |  |  | 0
Operations Log — issues recorded |  |  | 0
Operations Log — open (Not Started + In Progress) |  |  | 0
Operations Log — closed (Done) |  |  | 0
Improvement Backlog — recorded |  |  | 20
Improvement Backlog — Done |  |  | 0
Improvement Backlog — MVP scope |  |  | 0
Improvement Backlog — Later |  |  | 0
Monthly Review — Action Needed items |  |  | 0