## START HERE
Decision Log + Risk Register
One workbook used across the entire project to capture key decisions and risks. Add entries as they happen — not at end of phase. Saves hours of "why did we decide X?" discussions later and is gold during retrospectives.
When to add an entry
Sheet | When to use
Decision Log | Add a row when: scope is locked, package upgrade chosen, AI boundary set, human-only task agreed, key tool chosen, payment terms agreed, anything where you'd later wish you'd written it down.
Risk Register | Add a row when: a risk surfaces during discovery, a test fails in a worrying pattern, a security concern emerges, a client behaviour signals trouble, a dependency on a third party becomes visible.
At a Glance | Auto-computed summary. Open this when planning the next phase or preparing for monthly review — shows open decisions/risks needing attention.
Tip — entry hygiene
Decisions: write what was decided AND why. The "why" is what saves you 3 months later.
Risks: be specific. "AI may misclassify sensitive messages" is useful; "AI quality" is not.
Update status when reality changes. A risk that becomes a real defect → mark Realised + cross-link to Defect Log.
Reversibility on decisions matters most. One-way decisions deserve careful framing in the Context column.

## Decision Log
Decision Log
Add a row each time a key project decision is made. ID, Date, Phase, Decision, and Context are the minimum — others can be filled in later.
ID | Date | Phase | Topic | Decision (what was decided) | Context / Reasoning | Decided by | Reversibility | Status | Notes
D-001 | 2026-08-25 | Phase 1 | AI auto-send boundary | AI may draft replies but NEVER auto-send. Human approval required for every outbound message. | Client is risk-averse and operates in regulated (health) context. Approval workflow lowers risk and matches client comfort level (Q9 in Pre-Interview). | Client + PM | Costly to reverse | Active | Re-evaluate after 3 months of operation.
D-002 | 2026-09-10 | Phase 2 | MVP excludes Instagram channel | Defer Instagram DM intake to Phase 2 (next iteration). MVP covers email + website form only. | Instagram API access requires additional setup the client cannot complete in MVP timeline. Email + form already cover 80% of inbound volume. | Client + PM | Reversible | Active | Add to Improvement Backlog as candidate for managed-service expansion.
D-003 | 2026-09-01 | Phase 2 | Document extraction error tolerance | AI extraction accepted only if all required fields are present; any mismatch routes to human review before posting. | Document automation can introduce financial errors if unchecked data is posted. Human confirmation step protects data integrity. | PM | Reversible | Active | Re-evaluate per document type after 1 month of operation.
D-004 | 2026-09-05 | Phase 2 | Content automation — human approval mandatory before publish | No content automation may publish to any channel without explicit human approval of every draft. | Auto-publishing risks brand damage and incorrect messaging. Approval gate is non-negotiable across all content automation types. | PM + Client | Costly to reverse | Active | Review after 2 months; consider conditional auto-publish for pre-approved content types only.

## Risk Register
Risk Register
Add a row when a risk surfaces. Risk Level is auto-calculated from Likelihood × Impact: Low/Low = Low; High/High = Critical; mixed = Medium or High.
ID | Date | Phase | Risk description | Likelihood | Impact | Risk Level (AUTO) | Mitigation | Owner | Status | Notes / cross-ref
R-001 | 2026-08-25 | Phase 1 | AI misclassifies sensitive health inquiry as routine, sending generic auto-reply | Medium | High | High | Human approval workflow on ALL outbound replies; no auto-send in MVP; sensitive-keyword fallback to human review folder | PM | Mitigated | Cross-ref: D-001 (no auto-send)
R-002 | 2026-09-15 | Phase 3 | Client doesn't grant OAuth access to Gmail by build start, delaying Phase 4 | Medium | Medium | High | Send OAuth instructions 1 week before build start; offer to walk through together; escalate if no response within 3 days | PM | Open | Check by 2026-09-20
R-003 | 2026-09-01 | Phase 3 | AI extracts incorrect invoice amount or supplier; automation posts unvalidated data to accounting system | Medium | High |  | Human confirmation required before any write to accounting; validation module checks all required fields; error route on any mismatch. | PM | Open | Cross-ref: D-003
R-004 | 2026-09-05 | Phase 3 | Content automation publishes incorrect or off-brand post to client social channels without human approval | Low | High |  | Approval gate mandatory before every publish action; no auto-publish path in workflow; post-publish alert to owner. | PM | Mitigated | Cross-ref: D-004

## At a Glance
At a Glance (auto-computed)
Open this when planning a phase or preparing a monthly review. Counts come from the Decision Log and Risk Register sheets — keep those up to date.
Decision Log — by Status
Category | Meaning | Count
Active | Currently in force. | 4
Superseded | Replaced by later decision. | 0
Reversed | Decision was undone. | 0
Under Review | Being reconsidered. | 0
Total recorded | All decisions logged. | 4
Decision Log — by Reversibility (Active only)
Category | Meaning | Count
Reversible | Easy to change. | 2
Costly to reverse | Possible but expensive. | 2
One-way (irreversible) | Cannot undo. | 0
Risk Register — by Status
Category | Meaning | Count
Open | Risk active, no mitigation. | 2
Mitigated | Mitigation in place. | 2
Realised | Risk became real issue. | 0
Closed | No longer relevant. | 0
Accepted | Risk accepted, no mitigation. | 0
Total recorded | All risks logged. | 4
Risk Register — by Risk Level (Open + Accepted only)
Category | Meaning | Count
Critical | Highest priority. | 0
High | Watch closely. | 1
Medium | Manage normally. | 0
Low | Routine. | 0
Healthy project signal: Critical and High risks should be ZERO or actively mitigated. Any Open Critical risk is a stop-and-discuss signal.