## START HERE
AI Automation Managed Services — Master Overview / Index (v3)
One navigation and control file for the full PM lifecycle. Covers the 6-phase project cycle plus pre-engagement (Fit Check, Kickoff) and post-engagement (Retrospective) lifecycle tools, cross-phase tools (Decision Log, Risk Register), helpers (Pricing, Workflows Library), and client deliverable templates. v3 updated 2026-06-28.
Step | What to do | Use which file | Output
0a | Triage every prospect BEFORE committing time. Run the Fit Check to filter bad-fit projects. | PhaseX_Project_Client_Fit_Check | Verdict: GOOD FIT / PROCEED WITH CAUTION / DECLINE
0b | For approved prospects, capture kickoff info and pre-populate the framework. | PhaseX_Project_Kickoff_Wizard | Project Card + Pre-Population Map across files
1 | Collect client needs, risks, channels, sensitive areas. Use English or German tab. | Phase1_Discovery_MASTER (v5 EN-DE) | Discovery findings + internal package indication
2 | Move selected findings into Phase 2. Decide what's in MVP, Later, or Excluded. | Phase2_Scope_MVP_Design | Approved MVP scope
3 | Design exact workflow, tools, data fields, routing, approvals, security. | Phase3_Solution_Blueprint | Build-ready blueprint
4 | Build the MVP modules. Configure prompts, credentials, logs, error handling. | Phase4_MVP_Build | Working MVP
5 | Test normal, edge, sensitive, wrong-classification, and tool-failure cases. | Phase5_Testing_Validation | Go / No-Go decision
6 | Launch, monitor, support, report monthly. Improve as managed service. | Phase6_GoLive_Managed_Service | Live managed automation service
7 | Manage client-facing deliverables, approval gates, and external IP boundaries. | Phase7_Client_Communication_Deliverables | Approval gates passed + IP guarded
∞a | Log every key decision and risk as they happen — not at end of phase. | PhaseX_Decision_Log_Risk_Register | Documented decisions/risks; cross-phase traceability
∞b | Reference for workflow examples, decision-tree templates, Mermaid diagrams. | Helper_Example_Workflows_Library | Reusable workflow patterns
∞c | Compute setup + monthly quotes; ROI calculator; sanity checks. | Helper_Pricing_Calculator (v6) | Validated quote ready for client
∞d | Generate client deliverable Word documents from phase data via AI. | 5 Word templates + AI_Fill_Prompt_Guide.docx | Polished client-facing documents (PDF or DOCX)
∞e | Identify the correct automation category for the client's primary process. Validate package direction and align discovery and pricing inputs. | Helper_Automation_Category_Reference | Automation category confirmed; package direction and complexity adders aligned
7+ | Run within 1-2 weeks of go-live. Capture lessons. Feed into next project. | PhaseX_Project_Retrospective | Lessons learned + framework improvement ideas
Color legend (this index)
| Green | Project-phase steps (Phase 1-7) — sequential workflow
| Purple | Pre / Post-engagement lifecycle tools — bookend the project
| Yellow | Throughout — cross-phase tools used continuously
| Grey | Reference / fixed guidance

## Phase Cycle Overview
Project Lifecycle Overview (Pre → 6 Phases + 7 → Post)
The 6 working phases are the project spine. Pre/Post-engagement and Throughout-rows show the lifecycle tools that wrap around them.
Stage | Name | Main Question | Main Activity | Primary Output | Input From Previous | Client-facing? | Risk Focus | Next Stage Trigger
Pre-engagement | Fit-check / Kickoff | Should we take this project? And if yes, kick off cleanly. | Run Fit Check on prospect; Kickoff Wizard for approved projects. | GOOD-FIT verdict + Project Card | Lead / inquiry / referral | Internal | Bad-fit clients; messy starts | Verdict = GOOD FIT and Kickoff Card complete
Phase 1 | Discovery / Analysis | What does the client need? | Interview, collect facts, identify processes, channels, data sources, risks, pains, flags. | Discovery answers + product flags + package indication | Pre-engagement Project Card | Mostly internal + client interview | Do not promise solution too early | Discovery findings complete enough
Phase 2 | Scope / MVP Design | What exactly do we build first? | Convert findings into MVP scope: Yes / Later / No. | Approved MVP scope and boundaries | Phase 1 findings + flags | Can be summarized to client | Prevent scope creep | MVP scope approved
Phase 3 | Solution Blueprint | How will the automation work? | Design workflow, data fields, routing, tools, approvals, security. | Build-ready blueprint | Phase 2 scope decisions | Partly client-facing | Access, data, approval, fallback logic | Blueprint signed off
Phase 4 | MVP Build | Can we build the first working version? | Implement modules, prompts, credentials, CRM, logs, errors. | Working MVP automation | Phase 3 blueprint | Mostly internal | No hardcoded keys; safe build | MVP ready for testing
Phase 5 | Testing / Validation | Is it safe and reliable? | Test cases, AI validation, edge cases, errors, escalation. | Go / No-Go decision | Phase 4 working MVP | Can include client UAT | Wrong classification, auto-action risk | Go decision accepted
Phase 6 | Go-live / Managed Service | Can it run as a service? | Launch, monitor, support, report, improve. | Live managed service | Phase 5 approval | Yes | Operations, monitoring, rollback | Service stable for ≥1 month
Phase 7 | Client Comms & Deliverables | Is the client always seeing the right version? | Manage approval gates, IP boundaries, deliverable consistency. | Approval gates passed + IP guarded | Outputs from every phase | Yes — all client-facing artifacts | Leakage of internal IP; gate skips | Used continuously, not phase-gated
Throughout | Cross-phase tools | Are decisions, risks, pricing, and workflow patterns captured cleanly? | Update Decision Log + Risk Register as events happen. Use Pricing & Workflows helpers as needed. | Documented decisions/risks; valid quotes | Events from every phase | Internal (mostly) | Undocumented decisions; forgotten risks | Continuous — no end trigger
Post-engagement | Retrospective | What did we learn? What changes for next project? | Run within 1-2 weeks of go-live. Fill Retrospective sheet + Archive. | Lessons + framework improvements | Closed project | Internal | Patterns hidden by skipped retros | Retro complete and lessons logged

## File Index
Framework File Index (21 files)
All files in the AI Automation PM framework, grouped by lifecycle role. Filenames use the convention: Phase0-7 for sequential phases; PhaseX for cross-phase; Helper for reference workbooks; numbered 1_ to 5_ for Word client deliverables.
Category | File | Purpose | Format | When used | Status
Index | AI_Automation_PM_Phase0_Master_Overview_Index | Navigation hub for the framework. Lifecycle overview, file index, dashboard. | xlsx | Always open — your map | In Use
Pre-engagement | AI_Automation_PM_PhaseX_Project_Client_Fit_Check | 10-question triage. GOOD FIT / PROCEED WITH CAUTION / DECLINE verdict. | xlsx | Before saying yes to a prospect | In Use
Pre-engagement | AI_Automation_PM_PhaseX_Project_Kickoff_Wizard_P1-2-3 | 20-question intake. Project Card + Pre-Population Map for all files. | xlsx | After fit-check passes, before Phase 1 | In Use
Phase 1 | AI_Automation_PM_Phase1_Discovery_MASTER_v6_EN-DE | Discovery interview tools — English + German tabs. | xlsx | First client meeting + analysis | In Use
Phase 2 | AI_Automation_PM_Phase2_Scope_MVP_Design_v3 | MVP scope, priority scoring, in/out decisions. | xlsx | After discovery, before blueprint | In Use
Phase 3 | AI_Automation_PM_Phase3_Solution_Blueprint_v2 | Workflow design, routing rules, tools, security. | xlsx | After scope approval | In Use
Phase 4 | AI_Automation_PM_Phase4_MVP_Build_v2 | Build tracking — backlog, modules, prompts, credentials. | xlsx | During build | In Use
Phase 5 | AI_Automation_PM_Phase5_Testing_Validation_v2 | Test matrix, defect log, Go/No-Go checklist. | xlsx | After build complete | In Use
Phase 6 | AI_Automation_PM_Phase6_GoLive_Managed_Service_v2 | Go-live checklist, operations log, monthly review. | xlsx | Launch onwards (recurring) | In Use
Phase 7 | AI_Automation_PM_Phase7_Client_Communication_Deliverables_v2 | Approval gates, IP boundaries, deliverable policy. | xlsx | Throughout — reference for client comms | In Use
Throughout | AI_Automation_PM_PhaseX_Decision_Log_Risk_Register | Decision Log + Risk Register with L×I → Risk Level. | xlsx | Update as events happen — all phases | In Use
Helper | AI_Automation_PM_Helper_Pricing_Calculator_v10 | Quote calculator, ROI tool, package reference, sanity checks. | xlsx | After Phase 1 / 2 for indicative quote | In Use
Helper | AI_Automation_PM_Helper_Example_Workflows_Library | Workflow patterns, Mermaid diagrams, decision-tree templates. | xlsx | Phase 3 design reference | In Use
Helper | AI_Automation_PM_Helper_Automation_Category_Reference (= vd-pattern-catalogue) | Now built as the Pattern Catalogue: 4 groups / 19 sub-processes, every example, each with a Scope boundary. Confirms category direction during discovery. Lives in _VDAIA_Processes. | docx/pdf | Phase 1–2 (category confirmation); reference throughout | In Use
Deliverable | 1_Discovery_Summary_TEMPLATE | Word template — Discovery output for client. | docx | After Phase 1 | In Use
Deliverable | 2_MVP_Scope_Confirmation_TEMPLATE | Word template — MVP scope approval gate. | docx | After Phase 2 | In Use
Deliverable | 3_Solution_Blueprint_Summary_TEMPLATE | Word template — Blueprint approval gate. | docx | After Phase 3 | In Use
Deliverable | 4_Test_Results_Summary_TEMPLATE | Word template — Go/No-Go gate. | docx | After Phase 5 | In Use
Deliverable | 5_Monthly_Service_Report_TEMPLATE | Word template — Recurring managed-service report. | docx | Monthly during Phase 6 | In Use
Deliverable | AI_Fill_Prompt_Guide | Reference for generating client deliverables from Excel data via AI. | docx | Whenever a deliverable needs generating | In Use
Post-engagement | AI_Automation_PM_PhaseX_Project_Retrospective | Project retrospective + pattern analysis archive. | xlsx | 1-2 weeks post go-live | In Use
File Count Summary (auto)
1 | Total files | 21
2 | Excel workbooks (xlsx) | 14
3 | Word documents (docx) | 6
4 | Currently in use | 21
5 | Not used yet | 0
6 | Skipped / archived / N/A | 0

## Handoff Map
Stage-to-Stage Handoff Map
What flows from one stage to the next. The PM Control Action column shows how to keep the handoff clean (the #1 cause of project friction is bad handoffs).
From | To | Transfer These Outputs | Why It Matters | Decision Gate | Common Mistake | PM Control Action | Client Involvement
Lead / inquiry | Pre-engagement | Initial contact info + first impression of fit. | Pre-screening saves wasted time on bad fits. | Worth investing in fit check? | Skipping the fit check on "easy" leads. | Run the Fit Check before sending pricing. | Low
Pre-engagement | Phase 1 | Project Card + Pre-Population values for kickoff data. | Phase 1 starts informed, not from scratch. | Fit Check = GOOD FIT and Kickoff Card filled? | Starting discovery before kickoff is captured. | Use Pre-Population Map; fill Master Index Mini Dashboard. | Low
Phase 1 | Phase 2 | Needs, channels, pain points, risks, product flags, package indication. | Scope must come from real client answers. | Enough facts to define MVP. | Jumping directly to tool choice. | Convert every key finding into Yes/Later/No decision. | Medium
Phase 2 | Phase 3 | Approved MVP, exclusions, boundaries, approval rules. | Blueprint must not exceed agreed MVP. | MVP scope is stable. | Adding extra features during design. | Use In/Out Scope matrix as control. | Low / Medium
Phase 3 | Phase 4 | Workflow steps, tools, data map, routing, security, monitoring design. | Build team needs exact instructions. | Blueprint signed off. | Building without error handling or key plan. | Do build checklist before implementation. | Low
Phase 4 | Phase 5 | Working modules, prompts, credentials setup, logs, known limits. | Testing must cover real implementation. | Build complete enough to test. | Only testing happy path. | Prepare edge / sensitive / error cases. | Medium / High for UAT
Phase 5 | Phase 6 | Passed tests, defects closed, go/no-go, launch constraints. | Launch only when risks are controlled. | Go decision accepted. | Launching with unresolved critical defects. | Use Go-live checklist + rollback plan. | High
Phase 6 | Improvement cycle | Monitoring results, monthly review, client feedback, failures, new needs. | Managed service improves over time. | Monthly review completed. | Uncontrolled changes after launch. | Use improvement backlog and change control. | Medium
Phase 6 | Post-engagement | Final outcome, profitability, lessons, scope-creep history. | Retros are how the framework gets sharper. | Project is ≥1-2 weeks past go-live. | Skipping the retro — "I'll remember." | Run within 1-2 weeks; archive every retro. | None (internal)
Every phase | PhaseX Decision Log | Key decisions + reasoning + reversibility. | Avoids "why did we decide that?" debates 3 months later. | Whenever a notable decision is made. | Logging only big decisions; small ones matter too. | Update same-day; don't wait for phase end. | None (internal)
Every phase | PhaseX Risk Register | Risk + likelihood × impact + mitigation + owner. | Risks tracked = risks managed. | Whenever a risk surfaces. | Vague risks ("AI quality") instead of specific. | Be specific. Set status. Cross-link to Defect Log when realised. | None (internal)

## Package Logic Snapshot
Internal Package Logic Snapshot — aligned with Pricing Calculator
Package names match Pricing Calculator's Package Reference exactly, so Phase 1 Quick Diagnostic outputs feed cleanly into the Quote Calculator without translation.
Package | Typical Use | Discovery Triggers | Automation Methods | Human Approval | Risk Boundary | Good MVP Fit? | Typical Output | Notes
Basic Intake | Email/forms intake, rule-based routing, booking link, simple folders. Also: document or order notification routing to correct folder or owner; appointment request forwarding; basic data capture from web forms to a log. | One/two channels or data sources; highly repetitive process; no AI needed; client simply needs it sorted, routed, and logged — nothing more. | Rule-based routing; labels/folders; simple log. | Optional | No AI; no destructive action. | Very good | Classified and routed inquiries. | Smallest entry point. Often a stepping-stone to Basic+.
Basic+ AI Triage | AI classification + CRM/Notion log + folder routing + draft support. Also: AI field extraction from invoices or intake forms; auto-categorisation of expenses or support tickets; lead scoring from inbound form data. | Same as Basic, but client wants AI to classify, extract, or score — whether the input is a message, a document, a form, or a data record. Single input type; single AI action; human approves or reviews output. | AI classification; CRM logging; draft preparation. | Usually yes for first version | No auto-send; no sensitive advice. | Very good | Classified messages + CRM records + drafts. | MG Red Shift-style. The sweet spot for many small businesses.
Pro Multi-Channel | Email + social media + AI classification + draft replies + approvals. Also: multi-source document pipeline (email + PDF + form); content repurposing and scheduling workflow; multi-step data enrichment with review gate. | Multiple channels, data sources, or output steps; repeated patterns across them; client wants AI classification, extraction, or generation plus a structured approval step. Volume justifies the added complexity. | AI classification; AI drafts; multi-channel triage; approval queue. | Yes, especially outgoing replies | No auto-send for sensitive topics. | Good if integrations feasible | Draft replies + central intake dashboard. | Needs clearer channel access setup.
Managed Operations | Monitoring, CRM, reports, monthly improvements, ongoing support. Also: recurring KPI digest delivery; finance reconciliation runs; content calendar management; support ticket monitoring with sentiment escalation. | Client wants reliable, recurring automation with oversight — no missed items, structured reporting, and continuous improvement. Applicable to any automation category once core deployment is stable. | CRM workflows; reporting; reminders; audit logs; monthly optimization. | Depends on use case | Operational reliability and accountability. | Good after Basic/Pro stable | Managed operations dashboard. | Best recurring revenue layer.
Agentic Automation | Calendar/CRM actions; multi-step decisions; audit and governance. Also: document approval chains with conditional branching; lead routing based on score + rep availability; scheduled financial exception checks; content publishing sequences with conditional logic. | Client wants AI to make conditional decisions and take downstream actions — calendar, CRM, documents, finance, or content. Goes beyond classification or extraction into controlled, audited execution across multiple systems. | Agentic calendar/CRM actions; conditional workflows; approval gates. | Strictly required at start | High risk if uncontrolled. | Usually later, not first MVP | Controlled action automation. | Introduce only after trust & testing.
Build-and-Transfer | Automation built in client workspace and handed over. Applicable to any automation category when client requires full IP and operational ownership post-handover. | Client insists on full ownership and IP transfer, regardless of automation category. Commercial or legal position drives the package choice, not the automation type. | Depends on agreed workflow; built in client's account. | Per scope | Client takes operational risk after handover. | Specialist case | Full Make scenario + documentation. | Use 1.5x–3x setup multiplier; verify Fit Check first.

## Mini Dashboard
Project Control Mini Dashboard
Live project status — phases, dashboard fields, and cross-phase tool usage. The Kickoff Wizard's Pre-Population Map fills B4–B13 for you (rows 4-13). The 6-phase tracker stays as the project progress spine.
Control Item | Update When | - | - | Current Value / Notes
Client Name | At project start
Project Name | At project start
Current Phase | Weekly or after phase gate
Package Direction | After Phase 1 or Phase 2
Primary Automation Type | After Phase 1 — select from 10 categories
MVP Statement | After Phase 2
Go-live Target | After Phase 4 or 5
Main Risk | Every phase
Next Action | Every meeting
Owner | Every meeting
Phase Progress Tracker (6-phase project spine)
Update Status as each phase progresses. Start/End dates and notes are optional but useful for retrospectives.
Phase | Status | Start Date | End Date | Notes / Open Issues
Phase 1 — Discovery / Analysis | Not Started
Phase 2 — Scope / MVP Design | Not Started
Phase 3 — Solution Blueprint | Not Started
Phase 4 — MVP Build | Not Started
Phase 5 — Testing / Validation | Not Started
Phase 6 — Go-live / Managed Service | Not Started
Lifecycle Tools Status (cross-phase tool usage)
Track which lifecycle tools have been used for THIS project. Helps ensure nothing slips between the phases.
Tool | Status | Done Date | By Whom | Notes
Fit Check (PhaseX_Project_Client_Fit_Check) | Not Started |  |  | Pre-engagement triage; verdict logged.
Kickoff Wizard (PhaseX_Project_Kickoff_Wizard) | Not Started |  |  | 20-question intake + Project Card.
Decision Log + Risk Register (PhaseX) | Not Started |  |  | Updated throughout the project.
Pricing Calculator (Helper) | Not Started |  |  | Quote computed; sanity checks passed.
Workflows Library (Helper) | Not Started |  |  | Referenced during Phase 3 design.
Client Deliverables (5 Word templates) | Not Started |  |  | Sent at each approval gate.
AI-Fill Prompt Guide | Not Started |  |  | Used to generate client deliverables.
Retrospective (PhaseX_Project_Retrospective) | Not Started |  |  | Post-engagement, 1-2 weeks after go-live.
Project at a Glance (auto-computed)
Indicator | Value | - | - | Notes
Phases — Not Started | 6 |  |  | Phases not yet begun.
Phases — In Progress | 0 |  |  | Phases currently underway.
Phases — Done | 0 |  |  | Phases completed.
Phases — Blocked | 0 |  |  | Phases blocked — needs resolution.
Phases — Skipped | 0 |  |  | Phases intentionally skipped (rare).
Lifecycle Tools — Done | 0 |  |  | Cross-phase tools completed.
Lifecycle Tools — In Progress | 0 |  |  | Currently active.
Lifecycle Tools — Not Started | 8 |  |  | Yet to be used.
Dashboard fields filled | 0 |  |  | Out of 10 dashboard fields. <10 means some are blank.
Dashboard completeness | Empty |  |  | Empty / Partial / Complete.
Currently in | Not started |  |  | Derived from Phase Progress Tracker.